BIDDING  (Design-Bid-Build Process)

MBTA bid and award policy and procedures are detailed in the MBTA Procurement Manual.  Project Managers should be aware that the bidding schedule from advertisement to NTP can take 4 to 6 months plus the time it takes to prepare the required bidding documents such as pre-bid review control sheet, plans and specifications.

  - OVERVIEW

The MBTA Contract Administration Department within the Design & Construction Department is responsible for the procurement of all design and construction contracts. The MBTA procurement process complies with state and federal third party contracting requirements for competitive bidding and award. The department uses a variety of procurement methods, including emergency sole source, design-bid-build, design/build and construction manager (CM) at risk. The majority of D&C contracts are procured using the Design-Bid-Build process. For other project delivery methods, see their procurement manuals.  The Contract Administration Department is responsible for developing and maintaining a central File for bid documents for each project.  Construction contract procurement is also charged with the responsibility of maintaining procurement programs including monthly construction payments, change order processing, contract quantity variance reporting, contract close-out and preparation and furnishing of statistical contract data and summary reports to the appropriate state and federal audit agencies and in-house staff.

    - Contractor Prequalification

It is the policy of the MBTA that contractors must be prequalified in order to officially respond to a MBTA solicitation for contracts that exceed $1 million.

    - Emergency Sole Source

In the event that an emergency requiring a sole source procurement arises, Project Managers must work with the Law Department to prepare a justification memorandum.  The memorandum shall include allowable sole source justification as described in FTA Circular 4220.1F.  The sole source memorandum shall contain a signature line for approval by the person authorized to approve contracts as detailed in Section 3.

  - PRE-BID ADVERTISING

    - Obtaining Work Order Numbers

It is the Project Manager’s responsibility to obtain two work order numbers from the Budget Department as the first step to get a contract advertised.  The Work Order Numbers should be for:

- Work order number for the cost of the construction project; and

- Work order number for the cost of publically advertising the project.

    - Preparation of Bid Documents

The preparation of bid documents for advertising, prequalification of bidders and receipt and evaluation of bids is the responsibility of the Contract Administration Department. The PM must ensure that the necessary documents are provided to Contract Administration in a timely manner to support this process. The outline below provides an overview as to the construction procurement process for design-bid-build contracts.

The MBTA Procurement Manual also provides procurement procedures for Alternative Delivery Methods such as Design Build and CM at Risk are maintained in the Contract Administration Department (M.G.L. Chapter 149A.

(http://www.malegislature.gov/Laws/GeneralLaws/PartI/TitleXXI/Chapter14 9a .)

      - MBTA Project Manager transmits the construction specification at the 60%, 90% & 100% levels to Contract Administration for their review of the specification for compliance with MBTA policy, CSI format and State & Federal regulatory requirements. The A/E shall submit a table for review by Contract Administration, to show the spec sections being used are the most recent ones.

      - The four major sections of the specification: bid form, contract and bond forms, supplementary conditions and technical specifications are reviewed to ensure that each section is consistent with the MBTA’s requirements. The MBTA maintains standard contract specification guidelines on the MBTA web site, which consultants  download to initiate specification development. The MBTA Project Managers must ensure that the consultants are using the most up to date version of the specifications as required in the consultant professional services contract article II General Provisions.

      - At the 30% to 60% design phase, the PM shall start obtaining the documentation necessary to complete the pre-bid review control sheet (PRCS) needed to advertise the eventual construction contract. The PM must work with Contract Administration in the preparation of this PRCS. See Section 8 for more detail on the PRCS and construction procurement planning.

At 90% design, the PM may instruct the A/E to begin the Pre-Bid Review Control Sheet (PRCS) process. At 100% design, the consultant provides a final engineer’s construction cost estimate as detailed in the Project Controls Policy Manual.

As part of the 100% design review, the Project Manager should have completed the PRCS and all the associated memos. Refer to Section 8.3 for details.

The Project Manager must also coordinate the implementation of escrow bid documents and escrow memorandum into all contracts that are valued at/or above $1,000,000.00.

      - Upon final approval of the specification, the consultant provides an electronic copy to Contract Administration for distribution.

      - Contract Administration submits the request to advertise to the Director of Contract Administration with draft notice to bidder, engineer’s estimate, additional Independent cost estimates if applicable, and budget letter attached. The request is forwarded to the Assistant General Manager for Design and Construction for approval to advertise.

Generally, the bidding documents are the materials distributed to interested bidders, which form the basis for their bids. The bidding document consists of three major components.

- Contract Drawings and Specifications — These are the construction drawings and related materials prepared by the consultant (architect/engineer), which details how the project is to be built.

- Standard Forms — The bid package must include standard forms to be completed by the contractor. These forms include:

- Bid form

- Schedule of Bid Prices (note: AN items must be submitted by the PM and approved by the AGM.

- Bond forms

- Prequalification statements, if necessary

- Other forms as required

- Terms and Conditions — The package must also contain various legal terms and conditions to which the contractor must agree.  The MBTA has developed its "standard specifications" which includes the bidding and contract requirements (Instruction to bidders, general conditions) and division I — general requirements.

The Project Manager, Contract Administration and the consultant must all thoroughly review the contract specifications and related documents prior to advertisement.

Prior to advertising the “Notice to Bidders” Contract Administration must receive written approval by the Assistant General Manager for Design & Construction.

  - PRE-BID REVIEW CONTROL SHEETS (Exhibit 8-1)

    - Prior to advertising, a Pre-Bid Review Control Sheet must be completed and signed by the MBTA personnel listed below.  It is the responsibility of the Project Manager to route and track the progress and completion of the PRCS. Once fully signed, the PM delivers the document to Contract Administration to arrange for public advertisement.

- Manager of Environmental Affairs

- Project Manager

- Director of Design and Construction

- Director of Contract Administration

- Director of Project Controls

- Director of Quality Assurance

- AGM for Systemwide Accessibility (see 8.3.3)

- Chief Engineer

- AGM for Design & Construction

    - The PRCS is accompanied with the following memoranda:

- DBE participation (for federally funded projects only),

- QA/QC approval for paint systems

- Liquidated damages calculation

- Allowance items

- Real estate

- Risk management

- Compliance with Architectural Access Board regulations

- Sole source justification approvals (if applicable)

- Value engineering waiver (if applicable)

- Force account (if applicable)

- Risk analysis

- Constructability review

- Environmental review and approvals

    - In compliance with federal and state regulations pertaining to transportation for the elderly and for persons with disabilities, the ADA Certification form must also be signed.

    - The PBRC should be submitted to Contract Administration, (attention: Contract Documents Coordinator, Ten Park Plaza) with the final review specifications and appropriate documents and pertinent signatures.

The PRCS and required memoranda must be complete before Contract Administration will allow the project to be advertised. Please refer to Exhibit 8-2 for guidance on completing the PRCS.

Contract Administration must verify inclusion of the bid validation memorandum.

  - Advertising

The Request to advertise package is submitted to the Director of Contract Administration with a draft Notice to Bidders, Engineer’s Estimate and Budget Letter attached.

After the draft Notice to Bidders is approved, approval to advertise is obtained from the Assistant General Manager.

Once the Assistant General Manager’s approval to advertise is obtained, the final dates for bid opening, plans & specification availability, site tour and pre-bid conference are made.  Wage rates are also provided for inclusion in the contract.  The notice to bidders is sent to the Central Register for posting 21 days before the bid opening. The advertisement must appear in the Central Register for 14 days.  The MBTA publishes its notice to bidders at least thirty days prior to bid opening in the  MBTA’ Web site as well as in local newspapers and journals.  The MBTA usually allows for a 30 calendar day bid cycle from the date of advertisement to the date of the bid opening.  If a 21 day bid cycle is requested, the Project Manager must receive approval from Contract Administration and must notify ODCR.

For all projects, the Public Notice must contain the following information.

- A description of the project in sufficient detail to allow bidders to determine if they are qualified and wish to bid

- Funding source

- Specific class of work and pre-qualification requirements. The PM must work with Contract Administration to determine which classes of work are applicable.

- Where and when bidding documents can be obtained

- By when and to whom any Questions must be submitted in writing

- Where and when bids are due

- Estimated project value (for contracts greater than $1,000,000.00)

- Other state and federal requirements

  - Distribution of Bidding Documents

Contract Administration oversees and is responsible for the distribution of all bid documents. This involves:

- Providing bid documents to all requesting parties in the form of CDs.

- Maintaining a record of all contractors that receive the documents in the form of a plan holder’s list

- Distributing addenda to all parties who have received bid documents.

As contractors prepare their bids, any questions formulated by the contractors relating to the bid documents are sent in writing to the MBTA’s Project Manager. The Project Manager coordinates a response to the questions and any other clarifications to the documents and submits an addendum to Contract Administration for review.

Contract Administration reviews the addendum for conformance to MBTA policy and guidelines. Once the review is complete, Contract Administration obtains the Assistant General Manager for Design and Construction’s approval to issue the addendum. The addendum is then e-mailed to each plan holder with a return receipt request.

To avoid misunderstandings or protests in such cases, the bidder is requested to acknowledge receipt of all addenda in their bid forms.

  - Prequalification Procedures

The prequalification process is administered by the Contract Administration Department.  This process is required for all general contractors that wish to bid on MBTA contracts over $1,000,000.00.  The prequalification process can be found in the Contract Administrations Procurement Manual and on he website.

Any contractor proposing to bid on work with an aggregate value of one million dollars ($1,000,000.00) or more, must comply with the MBTA Prequalification Guidelines and Procedures, setting forth financial data as noted in Part IV “Financial Data” section of the Contractor Prequalification Statement.  To obtain prequalification, the MBTA considers financial capacity, work experience, adequacy of plant and equipment, and organization structure, as well as capabilities.  All corporations must show proof of registration with the Massachusetts Office of the Secretary of State to do business in Massachusetts.

For work with an aggregate value less than one million dollars ($1,000,000.00), post-qualification may be required. The information to be submitted after receipt of bids shall be similar to that required for prequalification. All bids submitted for work aggregating under one million dollars ($1,000,000.00) in excess of fifty thousand dollars ($50,000.00) will be accompanied by a letter of commitment from a surety company. This letter of commitment shall be in addition to any bid deposit.

A contractor may submit proposals for more than one project to be opened on the same or subsequent days. However, if the contractor is found to be the low bidder on one project, all subsequent bids which place the contractor him in the position of exceeding the contractor’s current capacity rating shall be subject to review.  The Authority reserves the right to accept or reject any such bids when such action is determined to be in the best interest of the Authority.

Subcontractors are approved post award by the MBTA Director of Quality Assurance.

  - Bid Deposits

Each bidder must submit with its bid a bid deposit equal to five percent of the amount of the bid.

The bid deposit may be in the form of a certified check, bank treasurers or cashier's check, cash or a bid bond from a licensed surety company.

  - Open Bids

All bids must be publicly opened and read at the time as stated in the publically advertised Notice to Bidders, and/or in any subsequent addenda.

Contract Administration reviews each bid to confirm that the low bidder has submitted a responsive and responsible bid.  This evaluation is further detailed in the MBTA Procurement Manual.

  - Pre-Award Conference/Designer Review Recommendation

After the bids are opened publicly, the engineer of record performs a bid analysis of all submitted bids to ascertain that the bids have met all of the technical requirements.  The engineer of record submits a bid analysis recommendation letter documenting their analysis of all of the bids, any questions that may have arisen out of the analysis, their recommendation that the lowest responsible bidder’s bid is fair and reasonable, and their recommendation to the MBTA to accept and award the contract to the apparent low bidder.  Contract Administration maintains a database comparing engineer estimates to actual bids.

In the event a bid is received that varies from the engineer’s estimate by more than 10%, the engineer shall include in the bid analysis a root cause analysis explaining the reasons for the variance.

Contract Administration also performs a bid analysis of the individual line items and required forms and certifications and makes a determination if the low bidder has correctly filled out the bid form.

For federally funded contracts, Contract Administration provides ODCR the low bidder’s DBE schedule of participation for review and concurrence that the low bidder meets the established goal.

Once Contract Administration’s review is completed and the engineer of record has performed its analysis, the apparent low bidder is invited to a pre-award conference to explain how they came up with their bid and answer any questions that may have arisen out of the bid analyses.  The MBTA Project Manager, the Director of Design and Construction, the engineer of record, and the apparent low bid contractor attend the pre-award conference.

Use of Bid Alternates - In the event bid alternates will be accepted, the Project Manger must notify Contract Administration in order to advance the award process.  The exercise of bid alternates impacts the determination of the low bidder..

Bid Cancellation – In the event the MBTA cancels or re-advertises a bid, the PM must provide the Director of Contract Administration memorandum providing the rationale for cancellation.

  - Authorization

Following the recommendation for award, the contract must be properly awarded, authorized, and executed in accordance with MBTA authorization levels.

All contracts are required to have a staff summary package prepared by the Project Manager with assistance from Superintendent of Administration and Finance.  The staff summary guidelines contained in section 3 of this manual explain the process of preparing staff summaries in order for a contract to be approved/authorized.

  - Contract Execution

Notice of Award - Contract Administration prepares a notice of award for signature by the General Manager and issues the notice of award to the low bid contractor.  The notice of award informs the contractor that the award has been voted upon and approved by the MBTA and instructs the contractor to coordinate with the Director of Contract Administration for execution of the contract.

Payment and Performance Bond - As part of the award process, the contractor signs the contract, the surety company signs and seals the performance and labor and materials payment bonds. The performance bond provides protection to the MBTA in the event of deficient work or default on the part of the contractor. The payment bond provides similar protection to the contractors’ subcontractors, guaranteeing they will be paid any monies owed them during the project. The contractor must submit to Contract Administration payment and performance bonds within 10 days of the date of the issuance of the notice of award.

Insurance Certificates - The insurance certificates are provided and a statement of management controls letter is furnished in accordance with the MBTA general conditions, article 5.4.  The contractor must submit to Contract Administration insurance certificates within 10 days of the date of the issuance of the notice of award.  The insurance certificates are reviewed by Contract Administration and the MBTA Risk Manager to ensure the requirements of the specification are met.

Escrow Bid Document - The contractor is also required to submit within five (5) days of the date of the issuance of the notice of award their escrow bid documents to the escrow agent.

Contract Document - The conformed copy is forwarded to the Risk Manager and General Counsel for "Approval as to Form".  Once signed by the General Counsel, the contract is forwarded to the General Manager for final signature.  The fully executed contract is returned to Contract Administration where it is dated and mailed to the contractor.

Notice to Proceed – The notice to proceed is issued upon General Manager approval of the contract.