## Slide 1: Red Line/Orange Line Improvement Program Update
July 16, 2018
Vehicle Procurement, Infrastructure Improvements,
State of Good Repair Improvements and Signal Upgrades

## Slide 2: OVERVIEW
The following summary provides an update to the Fiscal and Management Control Board on the progress of the Red Line/Orange Line Improvement Program; which includes new Vehicle Procurement, Infrastructure Improvements, State of Good Repair Improvements and Signal Upgrades.
This Program supports the MBTA’s goal to improve the Level of Service on the Red Line and Orange Line.

## Slide 3
Red Line/Orange Line Improvement Program
Orange Line
Red Line
NEW VEHICLE PROCUREMENT PROGRAM
INFRASTRUCTURE IMPROVEMENTS PROGRAM
SIGNALS UPGRADE PROJECTS
3
STATE OF GOOD REPAIR PROJECTS
$1,009.00M
$470.36M
$350.95M
$151.72M
Total $1,982.03M

## Slide 4: Red Line and Orange Line Schedule by Project
Construction
Design
LEGEND
Procurement
Interim Milestone to Support Vehicle Delivery - Completed
Interim Milestone to Support Vehicle Delivery
2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Pilot
1st Production
Pilot
Vehicle Procurement Program
OL Vehicles
RL Vehicles
Manufacturing/Delivery
Infrastructure Program – Orange Line
Wellington Yard Expansion Tracks 33-38
Orange Line Test Track
Wellington Maintenance Facility
Wellington Yard Rebuild
Infrastructure Program – Red Line
Red Line Test Track
Cabot Maintenance Facility & Cabot Yard Improvements
Completed
1st Production

## Slide 5: Red Line/Orange Line Schedule – Signals Upgrades
Design/Build
LEGEND
Procurement
MBTA Installation
Signal Upgrades Program - Orange Line
Mainline Signal Upgrades Project
Signal Enhancements
Signal Upgrades Program - Red Line
Mainline Signal Upgrades Project
Signal Enhancements
2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Completed
Procurement
2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022

## Slide 6: New Vehicle Procurement Program
Replace 120 Orange Line cars
32 new cars
Total = 152 vehicles
Replace 218 Red Line cars
34 new cars
Total = 252 vehicles
New Vehicle Procurement Program
Total Project Value: $ 1,009,871,671
Expenditure to date: $ 188,463,035 Carbuilder Percent Complete: 18.66%

## Slide 7: Vehicle Procurement Project Status – Current/Look Ahead
LEGEND
2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022
Pilot
1st Production
1st Production
Pilot
Vehicle Procurement Program
OL Vehicles
Manufacturing/Delivery
RL Vehicles
Design
  ● OL Pilot Car Qualification & Acceptance Testing - (through December 2018)
  ● OL Complete Vehicle FAI (Changchun) – (July 2018)
  ● OL Production Delivery from Springfield Facility Starts - (December 2018)
  ● RL Carbody Testing - (July 2018)
  ● RL Mock-up Display - (August 2018)
  ● RL Complete Vehicle FAI (Changchun) – (February 2019)
  ● RL Delivery of Pilot Cars - (March 2019)

## Slide 8: Orange Line Vehicle Procurement Project Status
Wellington - Qualification testing is ongoing along with training for the Operators. The current phase of testing is for the communication system and On-Board Video Recorder. Upon delivery of the remaining pilot cars, extensive 6 car testing will continue through the end of the year.
Changchun – The next 4 Pilot cars are completing qualification testing in China. Testing in Changchun includes brake rate testing at various loaded weights. These cars are scheduled for shipment from China in July with delivery to Boston in late August.

## Slide 9: Red Line Vehicle Procurement Project Status
Construction of the Red Line carshell for structural strength testing has been completed. Destructive Carshell Structural testing is scheduled to be performed from July to the first week of August.
Red Line Final Design Review meetings have been completed.
The Red Line Mock-Up was shipped to Boston in June and is scheduled for arrival in July and public display in August @ City Hall Plaza

## Slide 10: Production Vehicle Final Assembly – Springfield MA
Final assembly on the first four carshells is continuing in Springfield. HVAC units have been installed and installation of undercar equipment brackets is progressing.
In addition to the in-plant inspector who monitors production quality and workmanship the MBTA has now assigned a production surveillance supervisor. The MBTA continues its weekly audits of CRRCMA production and Q/A.

## Slide 11: Orange Line Projects: Wellington Yard Expansion Tracks 33 to 38
JF White
Construction NTP: 12/05/2016
Construction Substantial Completion:
  Contractual: 06/23/18
  Projected: 12/23/19 *
Construction Budget: $17,977,777
Construction Expenditures to Date: $6,169,114 Construction Percent Complete: 45%
*Adjusted to account for unforeseen environmental work
Installation of Turnouts
Underground Utilities Installed

## Slide 12: Orange Line Projects: Orange Line Test Track
LM Heavy
Construction NTP: 06/20/17
Construction Substantial Completion:
  Contractual: 09/11/18
  Projected: 08/17/18
Construction Budget: $5,867,000
Construction Expenditures to Date: $3,716,241
Construction Percent Complete: 91%

## Slide 13: Orange Line Projects: Wellington Maintenance Facility
Barletta Heavy Division
Construction NTP: 06/30/17
Construction Substantial Completion:
  Contractual: 08/04/20
  Projected: 08/04/20
Construction Budget: $72,582,000
Construction Expenditures to Date: $5,864,425 Construction Percent Complete: 16%
* Forecast completing on schedule
Electronics Building – Masonry Installed
Exterior Expansion – Piles Complete

## Slide 14: Orange Line Projects: Wellington Yard Rebuild
Barletta Heavy Division
Construction NTP: 05/31/18
Construction Substantial Completion:
  Contractual: 03/07/21
  Projected: 03/07/21
Construction Budget: $102,663,000
Construction Expenditures to Date: $0 Construction Percent Complete: 0%
  Wellington Yard Rebuild

## Slide 15: Red Line Projects: Red Line Test Track
Track Removed at Midland Street Bridge
T Wall Leveling Pads Installation
Barletta Heavy Division
Construction NTP: 11/17/17
Construction Substantial Completion:
  Contractual: 04/07/19
  Projected: 04/07/19
Construction Budget: $21,269,000
Construction Expenditures to Date: $432,705 Construction Percent Complete: 11%
* Forecast completing on schedule

## Slide 16: Red Line Projects: Cabot Yard & Maintenance Facility Improvements
LM Heavy/Lane Construction
Construction NTP: 07/20/18*
Construction Substantial Completion:
  Contractual: 12/22/21*
  Projected: 12/22/21*
Construction Budget: $213,817,000
Construction Expenditures to Date: $0 Construction Percent Complete: 0%
* Anticipated
  Cabot Yard & Maintenance Facility Improvements

## Slide 17: Signals Upgrade Projects Status
RFP Issued – 02/12/18
Proposer Meetings – 05/30/18
Proposals Due – 07/10/18
Public Price Opening – August, 2018
NOA – August 2018
NTP – September 2018
Substantial Completion RL – 10/05/21
Substantial Completion OL – 02/23/22
Red Line
RL Signaling and Train Control System Upgrade
RL Columbia Junction Phase II
Orange Line
OL Signaling and Train Control System Upgrade
OL South West Corridor Wayside Signal Replacement

## Slide 18: State of Good Repair Projects Status – Bridge Hardening
Status
Bridge Repairs
RL Substantial Completion – 11/01/18
OL Substantial Completion – 11/30/18
Long Fellow Approach – Interim Repairs
Substantial Completion – 12/31/18
Red Line
Bridge Repairs
Granite Spur-B-21-069 (A23)
Conley St.-B-16-136 (A38)
Fields Corner Busway-B-16-418 (A3N)
Victory Rd -B-16-134 (A36)
Geneva Ave-B-16-142 (A3D)
Long Fellow Approach - Interim Repairs
Orange Line
Bridge Repairs
Charles Street-M-01-003 (85)
Adams Street-M-01-002 (85J)

## Slide 19: Vehicle Procurement & Improvement Program Collaboration
Early involvement and collaboration with preparation of the Infrastructure Improvement Strategic Program Plan lead to:
  Definition of support categories: testing, storage, maintenance and reliability
  Interim milestones to support the vehicle arrival
  Scope in the Improvements Program to accommodate maintenance of the New Vehicle Features (overhead platforms, vehicle diagnostic room, Wifi, etc.)
Development of vehicle storage models to analyze storage impacts due to both New Vehicle commissioning schedule and construction contracts in the Infrastructure Improvements Program.
Pilot Vehicle Delivery Assessment and logistic coordination