## Slide 1: The RIDE Update
June 4th, 2018

## Slide 2: Summary
This presentation will cover:
  An overview of The RIDE’s recent service improvements across its key metrics
  An update on the TRAC transition with Transdev
  A summary of recent pilot growth statistics and a go-forward plan for Pilot 2.0
No board action is required at this time.

## Slide 3: RIDE PERFORMANCE Service has continued to remain strong through the transition period
Last 5 Months
Worst Performing Month in Past Year
Goal
* Preliminary results, data not fully reconciled

## Slide 4
CALL CENTER TRANSITION UPDATE Transdev invested significant time to make the transition a success
Transitioned Contracts
Engaged Stakeholders
Hired Employees
May
8-31
Summer
Planning for VTS Integration
Contract Awarded
Employees Contacted
April 30
June
Employee
Training
Transdev took full control of TRAC
June 1
Early Fall
Full VTS
Transition
Mobilization Team Onsite
May 7
Summer
Ongoing Operational Enhancements
Notes: Daily On-Site Mobilization Presence: Initial mobilization meeting held same week of award; Transdev team onsite daily since May 7th for observation and learning
Regular Debrief Sessions: Transdev has sat down with MBTA and Accenture to understand history of TRAC and prior issues to learn from past
Employee Engagement: All existing employees given opportunity to join Transdev and invited to Open House to meet existing Transdev employees. 143 out of XX existing TRAC employees onboarded; all key positions filled by new hires or interim Transdev staff
Staffing Level Monitoring: Weekly monitoring of employee retention and employee recruitment; current employee headcount is stable and adequate for transition. 250+ additional applicants beyond current employees provides a strong pipeline.
Stakeholder Engagement: Transdev met with RIDE Taskforce and made site visits to current Service Providers (NEXT and GLSS). Meeting this week with VTS.
Ongoing Enhancement: Transdev has begun to update training, improve SOPs, and address ongoing concerns from other stakeholders. All employees will undergo a full retraining and evaluation over the next two months.

## Slide 5: ON-DEMAND PARATRANSIT PILOT UPDATE Pilot growth has continued and a customer feedback survey was launched
Trip and ridership have continued to grow rapidly since our last update in February
6% monthly customer growth with 2,061 enrolled customers as of April
7% monthly trip growth with 12,204 trips taken in April
42% increase in total paratransit trips taken by pilot customers (both RIDE and pilot)
0 – 1% overall savings (program remains cost-neutral)
OPMI and OTA issued a survey to inform the design of “Pilot 2.0”
Customer feedback was solicited on the following:
Primary benefits of the pilot: Scheduling flexibility? Trip duration? Comfort?
Behavioral changes: What types of trips do customers take more of?
Price sensitivity: How might fare increases affect pilot utilization?
Continuing preference for RIDE: Why do some pilot members not use Uber/Lyft?

## Slide 6: ON-DEMAND PARATRANSIT PILOT UPDATE Current pilot will be extended to incorporate feedback and launch Pilot 2.0
Expected Timeline
June
Analyze OPMI customer survey results
Develop program changes (base fare, trip subsidy, trip allocation, etc.)
Summer – Fall
Implement TNC-TRAC integration once TRAC has been stabilized
Design and implement Pilot 2.0 utilizing customer and Taskforce input
Fall and Beyond
Assess impact of changes on customer mobility and overall savings
Make continuous improvements and changes to service

## Slide 7
Questions?