## Slide 1: FY18 Q3 MBTA Capital Program Update
May 14, 2018

## Slide 2: Major capital goals for FY18
Agenda
Execute approved FY18-FY22 Capital Investment Plan (CIP)
  Continue to accelerate investment in the core system to achieve and maintain a state of good repair within 15 years
  Execute major investment programs including the Green Line Extension, Red and Orange Line Improvements, Commuter Rail Safety and Resiliency (PTC), and AFC 2.0
  Award over $450M in new state of good repair construction contracts to ensure project pipeline that will drive future spend
Improve project controls, reporting, and processes and implement enterprise-wide project management information system
  Continue to implement e-Builder
  Development of EAC (Estimate-At-Completion) workbook to enhance program reporting

## Slide 3: Major Project Milestones Year to Date
Green Line Extension: $1 billion Design-Build contract awarded in November 2017 with notice to proceed in December 2017; first Green Line pilot cars arrived March 2018
First new Orange Line pilot cars arrived for testing in December 2017; construction began on Orange Line and Red Line infrastructure improvements
Positive Train Control hardware and software installation continues in advance of December 2018 deadline
AFC 2.0 contract awarded November 2017 and reached financial close in March 2018
State of good repair construction contract awards projected to be approximately $600M in FY18; over five times the amount awarded in FY16 and 83% percent higher than FY17
Capital Program Update

## Slide 4: Financial Overview of Capital Program
MBTA currently utilizes several metrics to measure the progress it is making against its capital plan, including:
  Cash spending (year-to-date);
  Spending on an accrual basis;
  Contract commitments, and
  Projects Underway
Cash Spending – keeping good track of the “paid-values” but not able to capture “earned-values”.
  YTD spending on a cash basis for the nine months ended 3/31/18 is $567M, $56M higher than the prior period.
Capital Program Update

## Slide 5: FY18 YTD Total Spending (cash basis)
Capital Program Update
FY18 YTD cash expenditures: $566.5M
 | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March | April | May | June
FY18 Actual ($M) | $47.8 | $56.9 | $41.0 | $59.3 | $80.9 | $66.6 | $100.7 | $53.2 | $60.2 |  |  | 
FY18 YTD ($M) |  | $104.8 | $145.7 | $205.1 | $285.9 | $352.4 | $453.2 | $506.3 | $566.5 |  |  | 
Note: Numbers may not sum due to rounding.

## Slide 6: Financial Overview of Capital Program
Spending on an Accrual Basis – captures work performed within the period but not paid. The MBTA will report spending on an accrual basis for all programs beginning in FY 19. This quarter, the MBTA is reporting on an accrual basis for key programs, including vehicle engineering, PTC, R/O line, and AFC 2.0.
Benefits include:
  Helps to explain variations to cash flow projections
  Provides timely tracking of planned vs. actual work performed
  Improves accuracy of Estimate-at-Completion (EAC) forecasts
  Helps improves future cash flow projections
  More accurately captures total capital investment
Capital Program Update

## Slide 7: FY18 YTD Total Spending (accrued basis)
Capital Program Update
Capital work complete but not yet paid
More accurately captures total FY18 investment

## Slide 8: Financial Overview of Capital Program
Commitments – As the MBTA ramps up its capital program, contract commitments is a key leading indicator and ensures a project pipeline that will drive future spend.
The MBTA is on track to award approximately $600M in new State of Good Repair (“SGR”) construction contracts.
The MBTA has also awarded $1.0B for Green Line Extension and $368M for AFC 2.0 this year.
Capital Program Update

## Slide 9: Commitments: MBTA Capital Program contract awards more than doubled in the past year
Capital Program Update

## Slide 10: Financial Overview of Capital Program
Projects Underway – Projects Underway (defined as projects with cash spending) is another leading indicator of how well the MBTA is executing its capital plan.
$4.2B of the MBTA’s $7.4B 18-22 Capital Plan is underway.
Going forward, 70% of FY19 projects (dollars basis) in the 18-22 CIP are underway.
Capital Program Update
Note: Projects underway are defined as projects with any actual cash spent to date.
FY18-FY22 5 Year Total: $7.4B
FY19 Total: $1.2B

## Slide 11: Enterprise Project Reporting
An Enterprise EAC Workbook has been developed for the MBTA providing a Project centric view that captures funding information by multiple funding sources, work order assignment, and overall project cost information, including ETC and EAC in one location
Benefits:
  Standardized Reporting Solution for the MBTA Enterprise
  Single source for overall Project Cost/Financial Reporting
  Project Budget/Funding Management in one location
  Transparency of monthly cost accumulation, ETC and EAC
  Accountability at all levels within the organization
  Disciplined and consistant approach for monthly/quarterly project reviews
EAC Workbooks will be included in e-Builder as a document, and the ETC will be updated via file share with external Design Consultants and General Contractors
EAC Workbooks will be used as the control/validation document as we move budget and cost management functionality into e-Builder
Project Management Information System Update

## Slide 12: PMIS Implementation Update:
Project Management Information System Update
Completed prototype reviews of MBTA future state configuration on 3/12/18
Phase 1 User Acceptance Testing was held the week of 4/02/18
Implemented e-Builder onto the AFC 2.0 project the week of 4/30/18
Completed and issued an Enterprise Phase 1 Solutions Document containing the agreed-upon configuration of Phase 1 configuration deliverables on 4/13/18:
Data Migration orientation sessions for Phase 1 Projects held the week of 4/16/18
Propagated the Phase 1 configuration from the prototype/development environment into the enterprise production environment the week of 4/23/18
Projecting to complete e-Builder Phase 1 scope on time (June 22, 2018) and under budget
Completed configuration to allow all new PayGo/Lock Box projects to begin using e-Builder as of May 01st
Configuration completed to allow new 2019-2023 CIP Projects to begin using e-Builder as of July 01st
GeoDOT interface - MBTA has determined that they can leverage and utilize the MassDOT GIS platform and license model for Linear Reference Mapping and data collection

## Slide 13: Next Steps:
Project Management Information System Update
Hold a formal e-Builder launch event, with General Manager message to the enterprise
  Targeting end of May timeframe
  Will publicize e-Builder enterprise branding for MBTA
Document management and control processes are a key next priority for the e-Builder implementation
  Completed several engagements with VE prime consultants (i.e. CH2M, LTK, & STV) to understand and map current document management processes
  We will continue mapping, optimizing and standardizing these processes over the next few weeks in preparing it for e-Builder implementation
Cataloguing and prioritizing business processes that will be created in e-Builder
  Process design will be executed in order of priority
Continue alignment with MBTA Lean initiative
Provide an overview of e-Builder implementation to American Council of Engineering Companies of Massachusetts (ACEC/MA) members during their May 23rd session
Notes: Published draft version of the CMS Functionality Report and have received valuable feedback from CMS power users. Currently in process of incorporating feedback into a final version of the report.

## Slide 14: High level project roadmap for accelerated implementation:
CMS Decommissioning *
Project Management Information System Update
Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
2018
2019
Projects, Documents, Roles, Project Creation
Cost Structure
Data Migration and Schedule
Cost Processes
Integration
Design Processes
Construction and Field Management
Capital Planning
Discontinue CMS Use
(end of 2018)
Full Implementation (end of 2019)
3 Implementation Streams:
Data Migration
Business Processes
Integration
*Keep database for Historical Info Only
CMS Decommissioning Planning
Phase 1
?
?

## Slide 15: Questions?
?

## Slide 16: Appendix
Appendix

## Slide 17: Capital contractual commitments entered in FY18 are building a strong pipeline for future work
Capital Program Update
SGR Construction Contract Description | Contract Value ($M)
Parking and Paving (On-Call) | $22M
Gloucester Drawbridge Replacement | $57M
Red Line Test Track | $21M
Commuter Track, Ties, & Switches (On-Call) | $24M
Commuter Rail Right of Way (On-Call) | $17M
Vegetation Removal (On-Call) | $1M
Back Bay Ventilation – Stair Pressurization | $5M
South Shore Garages | $64M
Fenway Portal Flood Protection | $8M
Wellington Yard Rebuild | $103M
Future awards | ~$279M
Total | $600M