## Slide 1: Draft CIP Update SFY 2019-2023 Joint Boards presentation
May 14, 2018
Draft 5/10/18

## Slide 2: Overview
CIP updates:
  Updates to approach
  Updated program budgets
  Updated spending by source
  Update on highlighted projects
Today:
  Need feedback on draft plan
  Approval to release for public comment and review

## Slide 3: Plan update: approach
Capital Planning Approach
Priorities: this CIP update maintains the strategy to invest first in the reliability of the transportation system, followed by modernization and, as a final priority, expansion. For the 2019-2023 CIP emphasis has shifted to modernization of our assets with our programmed investments. Reliability and Modernization combine to account for over 78% of our investments.
Programs: this CIP update has changed some programs to better reflect the needs of modal divisions or asset management. There are 67 investment programs. See details on the program changes. With this CIP, major multi-faceted projects such as Green Line Extension, South Coast Rail, among others, have now been shifted into their own programs.
Project selection: this CIP update reflects the changes made in 2018 to the weights used in the evaluation of modernization and expansion investments.
Planning for Performance Tool: the tool was revamped to more clearly reflect the CIP programs contained in this CIP update. The tool also updated data and analysis for some programs. The tool will continue to be updated in the future to forecast the performance of as many programs as possible.
CIP and STIP alignment: the development timelines of the CIP and STIP were aligned so that all applicable investments are identified in each document. This is important for the CIP to more accurately reflect regional priority projects identified by our MPO partners.
Project intake: a new tool was launched in 2017 to help our municipal partners initiate Highway Division projects to be considered for investment by MassDOT or their respective MPO. This tool streamlines and improves what used to be a paper-driven process, which required substantial manual entry of data. The tool will continue to be improved and will be expanded to other Divisions including the MBTA.
This is a one-year update
The majority of the CIP was set in motion in SFY 2018-2022
Adding SFY 2023
Over one third of the CIP is dedicated to projects with our municipal partners

## Slide 4: MassDOT spending by source
Projected sources (in millions) | FY 2019 | Total
Federal sources of funds |  | 
Federal Highway (FHWA) reimbursements | $611.8 | $3,792.1
Federal Transit (FTA) reimbursements | $4.6 | $24.1
Federal Aviation (FAA) reimbursements and grant draws | $37.0 | $209.6
Federal Rail (FRA) reimbursements and grant draws | $3.5 | $4.6
Subtotal federal sources | $657.0 | $4,030.3
Bond cap | $898.2 | $4,214.0
Accelerated Bridge bonds | $76.5 | $92.1
Rail enhancement bonds | $59.8 | $149.2
CARM | $24.2 | $190.1
Metropolitan Highway system (MHS) pay-go | $77.7 | $175.3
Gaming | $0 | $0.0
Western Turnpike (WT) pay-go | $30.2 | $105.0
Tobin Bridge (Tobin) pay-go | $40.9 | $232.1
Reimbursable and 3rd parties | $3.6 | $34.2
Municipal and local funds | $3.3 | $14.3
Public private partnerships | $0.0 | $0.0
Subtotal non-federal sources | $1,214.3 | $5,206.4
Total sources | $1,871.3 | $9,236.7
** Totals may not add due to rounding

## Slide 5: MBTA spending by source
Projected Sources (in millions) | FY 2019 | Total
Federal sources of funds |  | 
Federal Highway (FHWA) reimbursements | $49.0 | $109.9
Federal Transit (FTA) reimbursements and grant draws | $402.9 | $2,721.0
FTA Full funding grant agreement (GLX FFGA) | $92.6 | $827.7
Other federal funds | $4.3 | $5.9
Subtotal federal sources | $548.8 | $3,664.6
Bond cap (including lockbox) | $60.9 | $301.0
Accelerated Bridge bonds | $0.4 | $0.4
Rail enhancement bonds | $185.3 | $1,097.0
MBTA Revenue bonds | $207.0 | $1,854.5
Metropolitan Highway system (MHS) pay-go | $0.7 | $1.3
Gaming funds | $0.0 | $0.0
Municipal and local funds (GLX) | $0.0 | $75.0
Reimbursable and 3rd parties | $14.4 | $84.0
Positive Train Control (PTC) financing | $97.9 | $336.7
Pay-Go lockbox (MBTA) | $159.6 | $551.2
Capital maintenance fund | $4.6 | $5.4
Subtotal non-federal sources | $730.8 | $4,302.7
Total Sources | $1,279.6 | $7,971.0
** Totals may not add due to rounding

## Slide 6: Plan update: bond cap comparisons
Chart: Bond cap: SFY 2018-2022 plan versus SFY 2019*-2023 plan update
| SFY 2016 | SFY 2017 | SFY 2018 | SFY 2019 | SFY 2020 | SFY 2021 | SFY 2022 | SFY 2023
Prior actuals | 827.5 | 859.3
SFY 2018 plan | 822.1 | 884.1 | 879.1 | 855.4 | 855.5 | 905 | 875.8
SFY 2019 update | 879.1 | 895.4 | 890.5 | 912.5 | 857.5
$40.0
$35.0
$7.5
Although 2023 is a new fiscal year in this CIP update, $875.8 million (average of FY18-FY22 targets) is used as a comparison of 5th year bond cap funding.
Change in assumptions from SFY 2018-2022 plan to SFY 2019-2023 plan update

## Slide 7: Plan update: Central Artery/Tunnel Project Repair and Maintenance (CARM) eligible projects
Capital Investment Plan assumptions:
  Balance: $385.8M
  Available for investment: $241.7M
  Established by Chapter 10 Section 63A of the Massachusetts General Laws, the fund is for the repair and maintenance of Central Artery / Tunnel (CA/T) facilities not caused by ordinary or routine wear and tear
  CARM is funded through a series of settlement agreements between the Commonwealth of Massachusetts’ Attorney General and United States Attorney General for Massachusetts
CARM eligible maintenance and repair work has been ongoing in the CA/T.
Highway Division is actively working with FHWA to complete reimbursements for work completed in the tunnels over the past 15 years.
CARM is not intended to fund the full cost of needed investments in the CA/T tunnel system:
      Projects are partially funded from the CARM at a percentage between 60 – 80%
      Remaining funds for individual projects are drawn from the Metropolitan Highway System (MHS) pay-go capital
SFY2019 to SFY2023 projections were developed by the Highway Engineering section through a rigorous risk and project selection analysis

## Slide 8: Plan update: investments overview
Chart: Overall spending by priority
Overall:
The draft SFY 2019-2023 CIP update continues the investment strategy of the prior CIPs. A majority of funds go toward the reliability and modernization of our transportation system, with modest investments in expansion of the system.
Increase highlights:
Additional funding ($47.5 million) for Commonwealth (Port) project
$80 million increase for South Coast Rail (design and early action)
$723.6 million in program budget increases at MBTA such as:
  $40.8 million increase for PATI investments
  $242.4 million for Facilities
  $443.2 million for RL/OL investments, Commuter Rail Safety (PTC), AFC 2.0
Is it affordable?
More in revenue bond assumptions for MBTA
Anticipates obligating available federal-aid in all Divisions
  Assumes significant spend down of FTA carry over balances for MBTA
millions | SFY 2018- 22 | SFY 2019- 23 | Differences
Reliability* | $9,647.0 | $8,374.7 | -$1,272.3
Modernization | $3,247.1 | $5,004.3 | $1,757.2
Expansion | $2,148.1 | $1,957.1 | -$191.1
Chapter 90 | $1,000.0 | $1,000.0 | -
Planning, Enterprises Services, & Other | $902.1 | $842.5 | -$59.6
Five-year total | $16,944.2 | $17,178.6 | $234.4
Chart: Overall spending by priority
| 1/ Reliability | 2 / Modernization | 3 / Expansion | Planning & Enterprise Services | Chapter 90
Priority | 8374.6558 | 5004.3496 | 1957.0772 | 842.5352 | 1000
Chart: Overall spending by priority
*MBTA investments in R/O Line shifted from Reliability to Modernization
Chart: Overall spending by priority
| 1/ Reliability | 2 / Modernization | 3 / Expansion
 | 8374.6558 | 5004.3496 | 2014.8772

## Slide 9: Funding for municipalities
Chart: Annual funding available for municipal roadway investments (in millions)
| SFY19 | SFY20 | SFY21 | SFY22 | SFY23
Chapter 90 apportionments | 200 | 200 | 200 | 200 | 200
Municipal bridge | 9.02 | 14.2 | 13.88 | 8.44 | 4.46
Complete streets | 12.4 | 12.5 | 3.125 | 0.125 | 0.125
FHWA funds distributed by formula to MPOs | 229.93 | 238.5 | 243.332 | 248.286 | 253.709
Over one third of Highway Division state and federal funds in this plan update go to support investments in municipal roadways and bridges
Five-year total = $2.3 billion

## Slide 10: Plan update: program changes
Program changes
Highway Division / Design, Row, Environmental: program costs were allocated to individual CIP programs that these efforts support. Previously these investments were not represented within the individual program structure.
Highway Division / Bicycle/Pedestrian: costs associated with implementation of the Bicycle and Pedestrian modal implementation plans have been separated into a new program. This program reflects Bicycle and Pedestrian/multi-use path programs substantially funded with FHWA funds.
Highway / Allston Multi-Modal: this program reconstructs and realigns the Allston interchange to improve safety for all transportation modes: walking, cycling, driving, transit and to create a vibrant Allston neighborhood reconnecting sections to each other and to the Charles River. Finance plan is under development.
MBTA / Customer Experience and Technology: program supports investments in projects that modernize the system and enhance customers’ experience. Costs associated with this program were formerly included in System Improvements.
MBTA / Risk Management and Mitigation: this program’s name was modified to include investments related to OSHA and proactive security improvements. Program was formerly called Federal Programs and Mandates.
Highway Division / Retainage and Utility Payments: program costs were allocated to individual CIP programs that these efforts support. Previously these investments were not represented within the individual program structure.

## Slide 11
Program changes continued
MBTA / Process Improvements and Innovation: program supports investments that develop and implement projects that increase the efficiency and quality of the system through technology and other innovations. Program costs were formerly associated with System Improvements.
MBTA / AFC 2.0: program is the MBTA’s new integrated, reliable, and convenient fare payment and collection system to enable customers to pay fares by tapping contactless bank cards, mobile phones, and fare cards across the entire system. Costs associated with this program were formerly included in System Improvements.
MBTA / Red Line/Orange Line Improvements: program supports investments in vehicle and infrastructure needed to fully modernize the Red and Orange line fleets and achieve the service goal of three minute headways. Investments in Red Line/Orange Line improvements were included in 2018-2022 as part of other programs (Revenue Vehicles, Track Signals and Power among others)
MBTA / Commuter Rail Safety and Resiliency: program supports investments that improve the safety and resiliency of the commuter rail network, including the implementation of Positive Train Control (PTC).
MBTA / Expansion Projects: this program makes targeted expansions in order to improve access to transit, including the Silver Line to Chelsea and Blue Hill Avenue Station on the Fairmount Line.
MBTA / Green Line Extension: program includes the vehicles, stations and infrastructure to extend the Green Line from a relocated Lechmere Station in East Cambridge to Union Square in Somerville and College Avenue in Medford. Costs associated with this program were formerly included in the Expansion Projects program category

## Slide 12
Program changes continued
OTP / Bicycle and Pedestrian Modal Implementation: program supports investments to meet needs identified through the statewide bicycle and pedestrian planning efforts. The plans address critical needs around safety, accessibility, network connectivity and maintenance.
RMV / ATLAS: program improves RMV service delivery options by replacing the ALARS system. Program dedicated to one project and reduced program size reflects progress on the implementation of the new system. The anticipated completion is expected for 2021.
Rail / South Coast Rail: program reflects the Commonwealth’s commitment to move forward with the South Coast Rail project to more fully meet the existing and future demand for public transportation between Fall River/New Bedford and Boston, and to enhance regional mobility while supporting smart growth planning and development strategies in the affected communities.

## Slide 13: Plan update: program budget changes
Program | 2018-2022 program budget (in millions) | 2019-2023 program budget | Comments
Highway / Design, ROW, Environmental | $660.0 | $0.0 | Program costs allocated to appropriate individual CIP programs support by efforts
Highway / Retainage and Utility Payments | $50.0 | $0.0 | Program costs allocated to appropriate individual CIP programs
Highway / Facilities | $161.5 | $181.7 | Program includes allocation of $20.2 million in design/project management cost allocation
Highway / Intersection improvements | $160.7 | $180.8 | Program includes allocation of $20.1 million in design/project management cost allocation
Highway / Interstate pavement | $281.7 | $316.9 | Program includes allocation of $35.2 million in design/project management cost allocation
Highway / Non-interstate pavement | $543.9 | $611.9 | Program includes allocation of $68.0 million in design/project management cost allocation
Highway / Roadway Improvements | $150.0 | $168.8 | Program includes allocation of $18.8 million in design/project management cost allocation
Highway / Safety Improvements | $235.8 | $265.3 | Program includes allocation of $29.5 million in design/project management cost allocation
Highway / Tunnels | $350.0 | $393.8 | Program includes allocation of $43.8 million in design/project management cost allocation
Highway / Roadway Reconstruction | $1,261.0 | $1,418.6 | Program includes allocation of $157.6 million in design/project management cost allocation
Highway / Capacity | $273.9 | $308.1 | Program includes allocation of $34.2 million in design/project management cost allocation
Highway / Allston Multi-Modal Implementation | $0 | $16.0 | Program reflects investment in roadways, multi-modal bus and rail station, rail layover & yard, and pedestrian / open space
Program budget changes
The highlighted program budget updates do not reflect all budget updates, rather changes that are most noteworthy

## Slide 14
Program | 2018-2022 program budget (in millions) | 2019-2023 program budget | Comments
Highway / Bicycle and Pedestrian | $220.5 | $180.6 | Program includes allocation of $20.0 million in design/project management costs and reflects transfer of $60 million to new program
IT / Cyber and Information Security | $9.6 | $15.0 | Program increased to include compliance with Article 87 – Executive Office of Technology Services and Security (EOTSS) initiatives
MBTA / Accessibility | $224.2 | $265.0 | Program reflects increase in additional Plan for Accessible Transit Infrastructure Investments (PATI) investment
MBTA / Facilities | $112.6 | $355.0 | Program reflects increase in additional spending on bus maintenance facilities & Integrated Fleet and Facilities Plan (IFFP)
MBTA / Risk Management & Mitigation | $538.8 | $177.8 | Renamed program; program reflects investments in OSHA and security upgrades. PTC moved to Commuter Rail Safety and Resiliency.
MBTA/ Revenue Vehicles | $1,702.7 | $1,289.9 | Program reflects decrease since Red Line/Orange Line vehicles are now in their own program
MBTA / Track, Signals, and Power | $1,285.6 | $950.0 | Program reflects scope for RL/OL work now in separate program
MBTA / AFC 2.0 | $622.3 | $160.0 | Initiatives combined in 2018-2022 under System Improvements program; split into three different programs for 2019-2023
MBTA / Process Improvements and Innovation |  | $25.0 | 
MBTA / Customer Experience & Technology |  | $104.0 | 
Program budget updates continued
The highlighted program budget updates do not reflect all budget updates, rather changes that are most noteworthy

## Slide 15
Program | 2018-2022 program budget (in millions) | 2019-2023 program budget | Comments
MBTA / Red Line/Orange Line Infrastructure | $0 | $1,565.7 | Program includes vehicle procurements, signal work and infrastructure investments
MBTA / Commuter Rail Safety and Resiliency | $0 | $637.5 | Program reflects various safety and resiliency efforts underway on commuter rail network, including PTC
MBTA / Expansion | $1,587 | $59.0 | Program reflects remaining spending on existing non-GLX expansion projects (no new investments); 2018-2022 program included GLX investment which is now in its own program
MBTA / Green Line Extension |  | $1,364.5 | Program reflects GLX project cash flows which were included under expansion projects program in 2018-2022 plan
Transit / RTA Vehicle Replacement | $58.0 | $92.3 | Program reflects additional investment to address fleet asset condition
Rail / South Coast Rail | $0.0 | $108.0 | Program reflects funding for South Coast Rail project early construction activities (SFY 2019); was included under Track and ROW expansion in 2018-2022 plan. Finance plan under development.
Rail / Track and ROW expansion | $100.0 | $0.0 | Program previously included funding for South Coast Rail project; no funds programmed in 2019-2023 for other track and ROW expansion projects.
RMV / ATLAS | $102.1 | $61.5 | Reflects remaining spending on ATLAS implementation
Program budget updates continued
The highlighted program budget updates do not reflect all budget updates, rather changes that are most noteworthy

## Slide 16: Review of 2019-2023 projects and changes
The following tables highlight changes for projects worth $15 million or greater in total cost:
  Changes in cost (>10%) to total costs as compared to 2018-2022
  Changes to scheduled start of construction (one year or more)
  Deleted or unfunded projects as compared to 2018-2022
Cost drivers include:
  Additional inflation costs incurred when scheduled start of project shifts out
    Highway project costs include escalation by 4% to mid-point of construction (per guidance from FHWA)
    Conversely, if project construction is initiated sooner, inflation adjustment could reduce total project cost
  Scope changes to MassDOT projects
  Scope changes to MPO projects or regional target projects not under MassDOT control

## Slide 17: Plan update: project status
Project (in design) | 2018-2022 project cost (in millions) | 2019-2023 project cost | Comments
Highway / Weymouth-reconstruction – Route18 | $85.8 million | $62.3 million | Revised costs reflects updated estimate at completion due to schedule changes and other allowance items
Highway / Haverhill bridge replacement | $58.5 million | $117.5 million | Chosen alternate assumes full bridge replacement; 2018-2022 plan assumed only superstructure replacement
Highway / Lynn-Saugus bridge replacement | $57 million | $90.7 million | As design for structural, mechanical and electrical components advanced from 25% to 90%, the project cost increased. Design improvements were also added to an adjacent intersection after 25% design.
Highway / Rutherford Avenue | $133.4 million | $152 million | 2019-2023 cost reflects Boston programmed value in TIP; project is under design by the City of Boston
Highway / North Washington Street bridge replacement | $150.9 million | $185.6 million | Additional mitigation costs for off peak construction; construction start delayed one year adding additional inflation costs
Highway / Needham-Wellesley 6 bridge reconstructions | $154.6 million | $176.2 million | Revised costs reflects updated estimate at completion due to schedule changes and other allowance items
Highway / Roadway improvements Route138 - Canton | $13.2 million | $30.6 million | Initial conceptual estimate in SFY2018 CIP, project is under design and cost reflects inflation based on revised schedule
Project status – changes to project cost

## Slide 18: Plan update: project status
Project (in design) | 2018-2022 project cost (in millions) | 2019-2023 project cost | Comments
Highway / Fall River Route 79 Davol Street | $78.9 million | $93.9 million | Project is in a conceptual stage (Pre-25% design) with alternatives being evaluated based on FHWA and local concerns.
Highway / I-95 north interstate maintenance | $15.4 million | $20.4 million | Project delayed; cost increase reflects additional inflation based on anticipated start date
Highway / Charlemont Bridge rehabilitation | $26.8 million | $26.8 million | Highway is working with the local community to scope the appropriate level of investment to address regional traffic and mobility needs
Highway / Mount Auburn Street rehabilitation | $16.4 million | $19.4 million | Initial conceptual estimate, project cost increase reflects additional inflation based on anticipated start date
Highway / Fitchburg (Twin Cities Rail Trail) | $16.3 million | $20.8 million | Project delayed; inflation increase based on a new start date of FFY 2020 and additional scope changes based on railroad issues.
Project status – changes to project costs

## Slide 19: Plan update: project status
Project (active projects) | 2018-2022 project cost (in millions) | 2019-2023 project cost | Comments
Highway / Casey Overpass | $68.2 | $86.5 million | Increased in cost related to additional scope (station canopy) requested by the MBTA
Highway / Commonwealth Ave. bridge replacement | $68.3 million | $85.1 million | Increased in cost related to additional MBTA scope
Highway / AET implementation & toll plaza demolition | $199.6 million | $164.6 million | Prior CIP values included costs for both the implementation, demolition and ongoing systems maintenance costs. System maintenance costs were transferred to the operating budget in September 2017
Highway / Longfellow Bridge | $270.2 million | $306.7 million | Revised costs reflects updated estimate at completion due to settlements and other allowance items
Rail / South Coast Rail | $144 million | $176.8 million | Additional funds budgeted in FY 19 to cover design, permitting and early action items; finance plan for Phase 1 construction is under development
Project status – changes to project costs

## Slide 20
Project | 2018-2022 project cost (in millions) | 2019-2023 project cost 2019-2023 | Comments
MBTA / Red Line/Orange Line Infrastructure Improvements | N/A | $2,003.0 | Reflects integration of all RL/OL improvements projects into one program (infrastructure improvements, vehicles, track, signals and power, etc.) that were previously captured in other programs and projects
MBTA / North Station Draw 1 | $121.1 | $156.0 | Revised budget reflects updated cost estimate
MBTA / Lynn Station and parking phase II | $81.8 | $33.6 | Revised budget reflects updated scope focusing on urgent repairs only, primarily to the station
Project status – changes to project costs

## Slide 21: Plan update: project status
Project | 2018-2022 project cost (in millions) | 2019-2023 project cost 2019-2023 | Comments
Highway / Chelsea viaduct | $0 | $221.8 million | Project was added to the SFY2019 CIP to meet FHWA and Tracker targets for structurally deficient bridges.
Highway / Natick Route 27 bridge replacement | $0 | $32.3 | New project advanced to address improvements along Route 9 identified in the regional Long range Transportation Plan for Boston
Highway / Taunton interchange improvements at Routes 24 & 140 | $0 | $70.7 million | Project deferred during local casino development and has been programmed due to the need for improvements at this location associated with the South Coast Rail project
Highway / Interstate pavement resurfacing I-495 from Hopkinton to Southborough | $0 | $27.3 million | Recent inspection reports indicated significant pavement deterioration along the corridor. Project was advance to address these deficiencies.)
Highway / I-90 & I-93 micro silica overlay replacement - ramps | $0 | $20 million | This is the first of several contracts to replace micro silica pavement placed as part of the Central Artery Project with a new, non-porous pavement
Highway / Lighting repairs Ted Williams Tunnel (TWT) | $0 | $33.6 million | One of several projects that replaced the larger lighting project originally included in the 2018-2022 plan
Project status – new projects

## Slide 22
Project | 2018-2022 project cost (in millions) | Updated project budget/schedule 2019-2023 | Comments
Highway / Lighting repairs I-90/I-93 tunnels | $0 | $56 million | One of several projects that replaced the larger lighting project originally included in the 2018-2022 plan
Highway / Boston vent stack exterior replacement (Dewey Square) | $0 | $15.5 million | Facility requires an upgrade and improvements to address structural issues. Project was advanced to address these deficiencies.
MBTA / Automatic Train Control (ATC) implementation | $0 | $279.0 | Funds implementation of Automatic Train Control on the north side commuter rail lines, in coordination with Positive Train Control (PTC) project
MBTA / Green Line track upgrade | $0 | $130.4 | Supports full depth reconstruction of Green Line track to improve safety and reliability
MBTA / Bus maintenance facility | $0 | $125.0 | Initial funding for new or expanded bus maintenance facilities, consistent with Integrated Fleet and Facilities Plan (IFFP)
MBTA / System-wide wayfinding improvements | $0 | $63.0 | System-wide program to upgrade wayfinding and station signage to improve customer experience
MBTA / Hynes Station | $0 | $45.8 | Reflects all costs for the Hynes Station project tied to the Parcel 13 air rights project, including developer payments
Project status – new projects

## Slide 23
Project | 2018-2022 project cost (in millions) | Updated project budget/schedule 2019-2023 | Comments
MBTA / Procurement of bi-level commuter rail coaches | $679.8 | $658.5 | In the FY18-22 CIP, a total of $679.8 million was displayed as generic “revenue vehicle investments”, pending the completion of the fleet plan. The FY19-23 CIP includes eight near-term vehicle overhaul and procurement projects identified in the Integrated Fleet and Facilities Plan (IFFP), reflecting $819.9 million over the five-year CIP window and $1.6 billion in total. *note: mix of hybrid and electric technologies for future bus fleet will be determined by outcome of battery electric bus feasibility study and pilot
MBTA / Option order procurement of New Flyer Hybrid 40 ft. buses |  | $172.6 | 
MBTA / Procurement of 40 ft. buses – FY 2021-2025* |  | $514.7 | 
MBTA / DMA replacement |  | $103.4 | 
MBTA / Overhaul of Kawasaki 900 Series bi-level coaches |  | $66.9 | 
MBTA / Procurement of battery electric 40 ft. Buses and related infrastructure* |  | $52.9 | 
MBTA / Replacement of RIDE revenue vehicles |  | $23.5 | 
MBTA / Midlife overhaul of new Flyer Allison Hybrid 60 ft. articulated buses |  | $15.9 | 
Project status – new projects

## Slide 24
Project | 2018-2022 project cost (in millions) | Updated project budget/schedule 2019-2023 | Comments
MBTA / Occupational Health and Safety (OHS) implementation | $0 | $41.5 | Funds initial program development, implementation, personal protection equipment (PPE), and infrastructure improvements in support of OHS requirements
MBTA / Aquarium and Maverick emergency life safety egress and infrastructure | $0 | $32.0 | Supports a complete analysis of power, signals, track, and facilities for the Aquarium to Maverick corridor as well as immediate repairs to emergency egress and vent shafts at Aquarium and Maverick
Project status – new projects

## Slide 25: Plan update: project status
Project | 2018-2022 project cost (in millions) | 2019-2023 project cost 2019-2023 | Comments
Highway / Allston viaduct | $0 million | $16 million | MassDOT working with stakeholders on the design and permitting of this project; MassDOT has programmed $16 million to fund project design through to procurement phase
Highway / Middleboro Rotary |  |  | 25% design anticipated Winter of 2018; permitting activities ongoing with FHWA and other relevant agencies.
MBTA / Worcester Union Station conceptual design study | $3.0 | $3.0 | Design only
MBTA / Natick Center station accessibility | $2.2 | $2.2 | Design only
MBTA / Elevator program multiple locations design | $10.0 | $29.5 | Design only for redundant and replacement elevators at priority transit and commuter rail stations
MBTA / Bridges - design | $17.4 | $17.4 | Design for MBTA bridge program
MBTA / Longfellow approach | $5.3 | $5.3 | Design only
MBTA / Allston commuter rail layover facility | $0 | $8.5 | New Project - design only
Project status – design only

## Slide 26: Plan update: project status
Project | 2018-2022 project cost (in millions) | 2019-2023 project cost 2019-2023 | Comments
Highway / I-93 / I-95 North Interchange |  |  | Alternatives analysis and permitting activities ongoing with FHWA and other relevant agencies; requires a finance plan.
Highway / I-93 / I-95 South Interchange |  |  | Alternatives analysis and permitting activities ongoing with FHWA and other relevant agencies; requires a finance plan.
Highway / Bowker overpass |  |  | Alternatives analysis and conceptual design activities ongoing with relevant agencies; requires a finance plan.
Highway / McGrath Highway |  |  | Alternatives analysis and conceptual design activities ongoing; requires a finance plan.
Project status – design only

## Slide 27: Plan update: project status
Project | 2018-2022 project cost (in millions) | 2019-2023 project cost 2019-2023 | Comments
MBTA / Winchester commuter rail station | $34.8 | $34.8 | Partially funds total project budget of $53.8 million
MBTA / Newton commuter rail stations | $21.5 | $21.5 | Partially funds total project budget of $46 million
Project status – design and partial construc- tion

## Slide 28: Plan update: project status
Project | 2018-2022 project cost (in millions) | 2019-2023 project cost 2019-2023 | Comments
Highway / Reconstruction of I-90/I-495 interchange | $275.7 million | $310.3 million | Construction start delayed two years to 2023 for refinement of design alternatives, selection and environmental permitting; cost increase due to inflation and changes to scope related to wetland mitigation
Highway / Charlton-Oxford reconstruction on Route 20 | $54.1 million | $71.7 million | Construction delayed one year to 2021; additional costs for new Route 20/Route 56 connector roadway, additional retaining walls, storm water improvements, and more than three miles of guard rail/barrier upgrades to comply with new MASH standards. Additional costs also reflect inflation based on new start year
Rail / Springfield Union Station | $10.5 million | $10.5 million | Platform “C” will be completed in FY 19 (delay of one year); programmed spending reflects remaining spending on project ($6.5 million); Total cost of $10.5 million unchanged
Project status – schedule

## Slide 29: Plan update: project status
Project | 2018-2022 project cost (in millions) | Status change | Comments
Highway / Lowell Lord Overpass reconstruction | $15.9 million |  | MassDOT is funding a portion of the project in collaboration with the City of Lowell. Lowell is responsible for financing and design of the project. Funding is pending the completion of the City’s design and finance plan.
Highway / MHS tunnels lighting Project | $322 million | Replaced by two separate projects | Scope and constructability revised into a series of smaller investments. The first two of these investments are included in the CIP.
Highway / Cape Cod Gateway project | $0 | $10 million | MassDOT is completing a study related to transportation mobility and is transitioning project from Planning to Highway; funds are to continue design efforts in coordination with the Army Corps of Engineers.
MBTA / Revenue vehicle investment | $679.8 | Reallocated | Funding for revenue vehicles displayed in the FY18-22 CIP as “pending fleet plan” has been allocated to near-term priority projects
MBTA / Pay-Go funds | $382.0 | Reallocated | Pay-Go funds are treated as a funding source for the FY19-23 CIP and assigned to specific projects
Project status – other status changes

## Slide 30: Plan update: interactive format
Similar to last year the CIP document will be presented as a “story map,” providing users the opportunity to interact with CIP content
link

## Slide 31: Plan update: engagement for draft CIP update
10 public meetings across the Commonwealth
  Tuesday May 15th – Boston (Mattapan)
  Wednesday May 16th – Worcester (with Central Massachusetts MPO)
  Thursday May 17th – Barnstable & Springfield
  Monday May 21nd – Framingham & Quincy
  Tuesday May 22nd – Pittsfield (with Berkshire MPO)
  Wednesday May 23rd – Peabody
  Wednesday May 30th – New Bedford
  Thursday May 31st – Fitchburg
Online comment tools
  Comments accepted directly on proposed projects
  Emails & letters

## Slide 32: Plan update: additional iterations
Changes expected before update is released for comment
  MPOs have released all of their TIPs for public comment; those project lists have been incorporated into the draft CIP update project lists; changes not expected until CIP released for public comment
  Changes requested from May 9 CPC meeting and today’s meeting
Changes expected after update is released for comment
  MPOs have endorsed all of their TIPs; those project lists will be incorporated into the final draft CIP update
  Changes due to any responses to public comments
Changes expected after June CPC & Board meetings
  Changes that may be requested from CPC and at the Board meeting before publishing the final plan
DONE

## Slide 33: Next steps and discussion
Continue with mapping of investments and an equity analysis before the Joint Board votes to release for public comment
Finalize content in on-line format for review during public comment period

## Slide 34: SFY 2018 accomplishments by division Program by program description slides Presented by priority and division
Appendix

## Slide 35: SFY 2018 accomplishments
Reconstructed Runway 5-23 and Runway Safety Areas (RSAs) at Lawrence Municipal Airport
Installed security cameras at (5) public use airports to halt aircraft break-ins, and provide clear runway & gate visibility
Began the build-out (second floor addition) of the snow removal equipment building at Norwood Airport ($1.5 million)
  Eliminates need for a new airport administration (cost savings of $2.5 million)
Planned, developed and delivered several IT projects to support the go-live of ATLAS including:
  Creation of credit/debt card payment options
  Systems support to ensure simultaneous use of legacy ALARS system in parallel to ATLAS during implementation
Developed an electronic field inspection report application for Highway field engineers to standardize processes and procedures of recording and approving daily inspection reports
All electronic tolling (AET) successfully implemented November 2016; as of February 2017:
  156.8 M transactions processed
  86% of transactions processed with an E-Z Pass
92% of construction contracts completed on or under budget in FY17
2.2% of interstate pavement in poor condition in FY17, meeting current target of less than 5%
97% of the construction program spending on statewide reliability/maintenance and modernization investments was delivered
Green Line Extension Design-Build contract of $1billion was awarded in November 2017 with notice to proceed in December 2017; first Green Line pilot cars arrived March 2018
First new Orange Line pilot cars arrived for testing in December 2017; construction began on Orange Line and Red Line infrastructure improvements
Positive Train Control (PTC) hardware and software installation continues in advance of December 2018 deadline
AFC 2.0 contract awarded November 2017
State of good repair construction contract awards projected to exceed $450 million in FY18
  Three times the amount awarded in FY16 and 37 percent higher than inFY17
Aeronautics
Highway
Information Technology
MBTA

## Slide 36: SFY 2018 accomplishments continued
South Coast Rail
  Received approval for draft supplemental environmental impact report (DSEIR) for South Coast Rail project
    MEPA certificate issued March 30,2018; final anticipated June 15, 2018
  Achieved 30% design
Made asset improvements with the following investments:
  Purchased and distributed 33,000 tons of ballast stone
  Installed 77,000 crossties and 1,100 switch timbers
  Inspected 200 bridges and culverts
    Made major repairs to 17 bridges
    Replaced one bridge
    Replace three existing culverts
  Reconstructed and upgraded 19 grade crossings and made signal upgrades to 8 crossings
  Surfaced, lined, and tamped 210,000 feet of rail track (approximately 35 miles)
  Reconstructed track, paving, and electric power for Cape Flyer trainset at Hyannis Yard
  41,000 trucks have been removed from the road with completion of nine IRAP projects
ATLAS
  First phase went live on March 26, 2018
  Registry began offering federally compliant REAL ID credentials
Opened 3 new Service Centers in Brockton, Plymouth, and Leominster
Added 10 more AAA locations so that all 34 AAA locations in the state are offering Registry services
Rail
Registry of Motor Vehicles
Transit
Funded a total of 181 replacement vehicles for the RTAs
  45 >30 ft buses replaced
  135 <30 ft buses replaced
Funded the Lowell RTA’s Gallaher Intermodal Center (Terminal Improvement) project that improved customer service amenities – ticketing, seating, safety and security features)
Provided construction funding for year 2 of 3 for Pioneer Valley Transit Authority’s Cottage Street operations & maintenance facility

## Slide 37: SFY 2018 accomplishments continued
$872 M in expected reimbursements for municipal transportation improvements from FY15 through FY18
Program provides funding to all 351 cities and towns in the Commonwealth based on the formula established by the Legislature
  Road miles – 58.33%; Population – 20.83%; Employment – 20.83%
Chapter 90
Complete Streets
Municipal Bridge
A total of $21.2 M has been awarded for 48 municipal projects since inception (FY17)
  36 awards in March 2017 for $16 M
  12 awards in January 2018 for $5.2 M
$4.2 M technical assistance grants have been awarded to 112 municipalities
$27.4 M in construction grants have been awarded to 71 municipalities ($23.2 M in executed construction grants)
152 municipalities have approved Complete Streets policies as of January 2018

## Slide 38: Reliability investments by program
Chart: 
| Transit / RTA Vehichle Replacement | Transit / Technical Assistance | Transit / RTA Facility and Vehicle Maintenance | Transit / Mobility Assistance Program | RMV / Operations Management | Rail / Track and Right-of-Way Reliability | Rail / Vehicle Reliability | Rail / Grade Crossings | Rail / Facility Reliability | Rail / Bridges | MBTA / Track, Signals, and Power | MBTA / System Upgrades | MBTA / Facilities | MBTA / Stations | MBTA / Revenue Vehicles | MBTA / Bridges and Tunnels | Information Technology / Asset Management | Information Technology / Cyber/Information Security | Information Technology / Digital Infrastructure | Information Technology / Desktop Experience | OTP / Pre-Apprenticeship | Highway / Tunnels | Highway / Safety Improvements | Highway / Roadway Improvements | Highway / Non-Interstate Pavement | Highway / Municipal Bridge | Highway / Interstate Pavement | Highway / Facilities | Highway / Equipment | Highway / Bridge | Highway / All-Electronic Tolling | Aeronautics / Airport Capital Improvement | Aeronautics / Airport Pavement Management System
Five-Year Program Size | 92300000 | 10000000 | 17450000 | 50100000 | 1100000 | 138250000 | 4700000 | 36500000 | 16725000 | 56200000 | 950000000 | 235000000 | 355000000 | 400800000 | 1289900000 | 544650000 | 15500000 | 15000000 | 19900000 | 9100000 | 4631843 | 393750000 | 265275000 | 168750000 | 611887500 | 50000000 | 316912500 | 181687500 | 75000000 | 2281725000 | 0 | 146000000 | 123300000
Aeronautics / Airport pavement management system
Aeronautics / Airport capital improvement
Highway / All-electronic tolling
Highway / Bridge
Highway / Equipment
Highway / Facilities
Highway / Interstate pavement
Highway / Municipal bridge
Highway / Non-interstate pavement
Highway / Roadway improvements
Highway / Safety improvements
Highway / Tunnels
OTP/ Pre-apprenticeship
Information Technology / Desktop experience
Information Technology / Digital infrastructure
Information Technology / Cyber/information security
Information Technology / Asset management
MBTA / Bridges and tunnels
MBTA / Revenue vehicles
MBTA / Facilities
MBTA / Stations
MBTA / System upgrades
MBTA / Track, signals, and power
Rail / Bridges
Rail / Facility reliability
Rail / Grade crossings
Rail / Vehicle reliability
Rail / Track and right-of-way reliability
RMV / Operations Management
Transit / Mobility assistance program
Transit / RTA facility and vehicle maintenance
Transit / Technical assistance
Transit / RTA vehicle replacement
Five-year program budget in millions
Aeronautics | Highway | IT | MBTA | Rail | RMV | Transit | Total SFY19-23
$269.3(millions) | $4,411.6 | $59.5 | $3,775.4 | $252.4 | $1.1 | $169.9 | $8,943.7

## Slide 39: Reliability programs for Aeronautics
Airport Pavement Management System
This program maintains the quality of pavement “inside the airport fence” at an adequate level. This program is necessary to continue safety and maintenance programs at public-use airports.
Program purpose and need statement:
Program performance:
Tracker target*
2018 – 72% average PCI; 2020 – 85% average PCI; Long term – 85% average PCI
PfP tool forecast
  87 average PCI for airport pavement by 2023
FY2019-2023 program budget:
$123.3 million over five years
Airport Capital Improvement
This program includes a full range of airport state of good repair projects. This program is necessary to continue safe and efficient airport operations and services.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
  Not forecasted in PfP tool
FY2019-2023 program budget:
$146.0 million over five years
Other indicators
  80% of vegetation management work planned is completed each year.
* Tracker targets published in MassDOT’s Annual Performance Report, November 2017

## Slide 40: Reliability programs for Highway
All-electronic tolling
This program converted the I-90 corridor from the New York border to Boston from a cash, toll booth system to a cashless system. Included in the program is the demolition of the former toll booths and realignment of exits and interchanges on the I-90 corridor.
Program purpose and need statement:
Program performance:
Tracker target
  2018 – 90%; 2020 – 92%; Long term - 95% E-Z Pass payment rate (vs. pay-by-plate)
PfP tool forecast
  Not forecasted in PfP tool
FY2019-2023 program budget:
$66.6 million – full implementation achieved; no spending in 2019-2023; program will be closed
Bridge
This program maintains, reconstructs and replaces state and municipally owned bridges across the Commonwealth.
Program purpose and need statement:
Program performance:
Tracker target
2018 - <14%; 2020 - <13%; Long term <10% NHS deck area in structural deficiency
PfP tool forecast
Under development
FY2019-2023 program budget:
$2,281.7 million over five years
Other indicators
Other indicators
  To be determined
  To be determined

## Slide 41
Equipment
This program makes routine purchases of vehicles, equipment and other capital assets. This program is necessary for the daily operation of the department.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
  Not forecasted in PfP tool
FY2019-2023 program budget:
$75.0 million over five years
Facilities
This program maintains, repairs and replaces buildings, salt sheds, garages, vent buildings, and telecommunications and other systems owned by the Highway Division.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$181.7 million over five years
Other indicators
Other indicators
  To be determined
  To be determined

## Slide 42
Interstate Pavement
This program resurfaces and performs related work on the interstate system. This program is necessary to improve pavement conditions.
Program purpose and need statement:
Program performance:
Tracker target
  2018 – 98%; 2020 – 88%; Long term - 99% of pavement in good or excellent condition
PfP tool forecast
Under development
FY2019-2023 program budget:
$316.9 million over five years
Municipal Bridge
This program assists municipalities in repairing and replacing town owned bridges with a span length of less than 20 feet.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$50.0 million over five years
Other indicators
Other indicators
  Number of inspections completed
  To be determined; set in accordance w/ federal performance requirements

## Slide 43
Non-Interstate pavement
This program resurfaces and performs related work on non-interstate roads owned by MassDOT. This program is necessary to fulfill system wide maintenance contracts to improve pavement condition and also includes site-specific projects.
Program purpose and need statement:
Program performance:
Tracker target
  2018 – 62%; 2020 – 62%; Long term - 62% of pavement in good or excellent condition
PfP tool forecast
Under development
FY2019-2023 program budget:
$611.9 million over five years
Roadway improvements
This program supports pot hole, fencing, guardrail, and sidewalk maintenance, repairs and other related improvements on non-interstate, state owned roadways. This program also includes federally funded storm water retrofit projects. This program is preventative in nature, and is necessary to maximize the useful life and condition of roadways.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$168.8 million over five years
Other indicators
  To be determined; set in accordance w/ federal performance requirements
Other indicators
  To be determined

## Slide 44
Safety Improvements
This program repairs traffic signals, highway lighting systems, impact attenuators, traffic signs and pavement markings. This program is necessary to provide a safe roadway network for Commonwealth residents and visitors.
Program purpose and need statement:
Program performance:
Tracker target
  2018 – 0.63 fatalities; 6 injuries*
  2020 - 0.62 fatalities; 6 injuries*
  Long term – move to zero
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$265.3 million over five years
Tunnels
This improves lighting, life safety systems and tunnel infrastructure within the tunnel network.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$393.8 million over five years
Other indicators
  Crash cluster; crash data
Other indicators
  To be determined
*Tracker target per 100 million vehicle miles traveled (VMT)

## Slide 45: Reliability programs for IT
Desktop Experience
This program delivers best in class, highly resilient technologies and services related to desktop and personal computing, conformance and mobile solutions/devices, and network and internet connectivity. This program is necessary to maintain best practices and state of good repair in desktop IT at MassDOT.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$9.1 million over five years
Digital Infrastructure
This program does a range of digital infrastructure work, including state of good repair hardware upgrades and support of operations in the Cloud. This program provides a modern, application-independent information architecture. This program is necessary to meet MBTA’s and MassDOT’s technology goals by sustaining the core computer, storage, telecommunications and network infrastructure.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$19.9 million over five years
Other indicators
Other indicators
  Monitor level of state of good repair – age of equipment, engineering performance, latest software releases, help desk support requests.
  Monitor level of state of good repair – age of equipment, engineering performance, latest software releases, equipment uptime statistics.

## Slide 46
Cyber/Information security
This program keeps IT infrastructure and software compliant with best practices and digital security standards to protect both agency and customer data and will comply with Article 87 – EOTSS initiatives. This program is necessary to maintain customer confidence when making secure transactions.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$15.0 million over five years
Asset Management
This program delivers tools and processes to document, report on and manage MassDOT assets. These tools provide data on the asset life cycle. This program is necessary to maintain the reliability of Commonwealth assets by supporting a consistent approach to asset review and remediation.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$15.5 million over five years
Other indicators
Other indicators
  Security Awareness Training taken by all employees annually. Comprehensive policies and controls in place. 100% PCI compliance.
  All DOT assets recorded and monitored for state of good repair. Minimize incident reports.

## Slide 47: Reliability programs for MBTA
Bridges and tunnels
This program repairs, reconstructs and replaces MBTA commuter rail and transit bridges and tunnels system-wide.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$544.7 million over
five years
Revenue vehicles
This program rehabilitates and replaces the MBTA revenue fleet, which includes commuter rail, heavy rail, light rail, bus and ferry units.
Program purpose and need statement:
Program performance:
Tracker target
  % of units beyond useful life benchmark
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$1,289.9 million over
five years
Other indicators
TAM requirement*
  % of revenue vehicles that meet or exceed the useful life benchmark**
  Number of structurally deficient bridges that have a condition rating under 4 points on the Pontis Scale*
*Pontis is a bridge management system licensed by AASHTO (American Association of State Highway and Transportation Officials) to store the condition of bridge structures. Pontis rates bridge condition on a scale of 1 to 9 with 9 being new.
*Federally Mandated Transit Asset Management (TAM) Requirement
**Useful Life Benchmark (ULB) is defined as the expected lifecycle or the acceptable period of use in service of a capital asset for a particular transit provider’s operating environment.

## Slide 48
Facilities
This program rehabilitates and upgrades maintenance and administrative facilities that support transit operations.
Program purpose and need statement:
Program performance:
Tracker target
  % of facilities with condition rating <3.0 in TERM* scale
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$355.0 million over five years
Stations
This program rehabilitates and upgrades MBTA stations (e.g., commuter rail, commuter boat, subway and bus stations).
Program purpose and need statement:
Program performance:
Tracker target
  % of facilities with condition rating <3.0 in TERM* scale
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$400.8 million over five years
TAM requirement*
TAM requirement*
  % of facilities rated <3.0 on TERM** scale
  % of facilities rated <3.0 on TERM** scale
*Federally Mandated Transit Asset Management (TAM) Requirement
**FTA TERM (Transit Economic Requirements Model) condition assessment scale of 1-5, in which an asset in need of immediate repair or replacement is scored as one (1), whereas a new asset with no visible defects is scored as five (5)
*Federally Mandated Transit Asset Management (TAM) Requirement
**FTA TERM (Transit Economic Requirements Model) condition assessment scale of 1-5, in which an asset in need of immediate repair or replacement is scored as one (1), whereas a new asset with no visible defects is scored as five (5)

## Slide 49
System upgrades
This program upgrades a wide range of MBTA systems including communications, security, computer technology, fare collection, asset management and environmental remediation systems. It also rehabilitates non-revenue vehicles and equipment.
Program purpose and need statement:
Program performance:
Tracker target
  Non-revenue vehicles: % of vehicles beyond Useful Life Benchmark
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$235.0 million over five years
Track, signals, and power
This program rehabilitates, replaces and upgrades track, signal and power assets across the commuter rail and transit system.
Program purpose and need statement:
Program performance:
Tracker target
  % of track segments with performance restrictions
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$950.0 million over five years
TAM requirement*
TAM requirement*
  % of track segments with performance restrictions
  % of non-revenue service vehicles exceeding Useful Life Benchmark
* Federally Mandated Transit Asset Management (TAM) Requirement
* Federally Mandated Transit Asset Management (TAM) Requirement

## Slide 50: Reliability programs for OTP/ODCR*
Pre-Apprenticeship
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$4.6 million over five years
Other indicators
  To be determined
This program, for which MassDOT is partnering with a number of stakeholders, facilitates the introduction of additional pre-apprentices to skilled trades within our construction program. This program is necessary to provide low-income and other disadvantaged communities with access to training and employment opportunities within the construction trades. Program managed by MassDOT’s Office of Diversity and Civil Rights Diversity (ODCR).
*ODCR is under Planning (OTP) & Enterprise Services

## Slide 51: Reliability programs for Rail
Bridges
This program repairs or replaces bridges to avoid deterioration, keep or restore class of line, or maintain utility. Prioritization of projects within this program reflect most recent inspections, type of usage (ex: hazardous cargo), and any contractual or regulatory requirements for action.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$56.2 million over five years
Facility reliability
This program repairs or replaces rail facilities, specifically rail yards and stations, to avoid deterioration or maintain the facility’s utility. Prioritization of program projects will reflect condition reports, type of risk/usage, and any contractual or regulatory requirements for action. This program is necessary to maintain a safe and reliable rail system.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$16.7 million over five years
Other indicators
Other indicators
  To be determined
  To be determined

## Slide 52
Grade crossings
This program repairs or replaces grade crossings to avoid deterioration, keep or restore class of line, or maintain the crossing’s utility. Prioritization of projects in this program will reflect federal guidelines, most recent inspections, type of usage (ex: hazardous cargo), and any contractual or regulatory requirements for action. This program is necessary to maintain a safe and reliable rail system.
Program purpose and need statement:
Program performance:
Tracker target
  1.79 highway-rail incidents/1000 grade crossings
PfP tool forecast
54% of grade crossings in desired state
FY2019-2023 program budget:
$36.5 million over five years
Vehicle reliability
This program repairs, replaces, or acquires rail equipment (locomotives, coaches, ballast cars, light duty vehicles, etc.) to facilitate reliable service, avoid deterioration, or support activities to maintain or restore class of line. This program is necessary to maintain the rail system in good condition.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$4.7 million over five years
  Approximately 20 grade crossings per year can be improved at this funding
Other indicators
Other indicators
  To be determined

## Slide 53
Track and right-of-way reliability
This program repairs or replaces assets within the rail right of way (typically ties, rail, ballast, culverts, switches, etc.) to avoid deterioration, keep or restore class of line, or maintain the line’s utility. Prioritization will reflect most recent inspections, type of usage (ex: hazardous cargo), and any contractual or regulatory requirements for action. This program is necessary to maintain a safe and reliable rail system.
Program purpose and need statement:
Program performance:
Tracker target
  26,000 ties repaired per year
PfP tool forecast
26,000 ties repaired per year
FY2019-2023 program budget:
$138.3 million over five years
Other indicators
  To be determined

## Slide 54: Reliability programs for RMV
Operations Management
This program maintains and improves existing operating systems to support service delivery, application platforms, and electronic records retention systems.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$1.1 million over five years
Other indicators
  To be determined

## Slide 55: Reliability programs for Transit
Mobility Assistance Program
This program purchases vans and related equipment used to provide transportation for the disabled and elderly by Councils on Aging, the RTAs and non-profits.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$50.1 million over five years
RTA facility and vehicle maintenance
The program addresses the maintenance, rehabilitation and upkeep of existing RTA facilities or vehicles.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker - facility condition (range)
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$17.5 million over five years
  Number of organizations who attended a training to participate in M.A.P.
Other indicators
Other indicators
  To be determined

## Slide 56
Technical assistance
This program is used to provide technical assistance to support the transit program (grants management systems, vehicle inspections, etc).
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$10.0 million over five years
RTA vehicle replacement
This program replaces existing Regional Transit Authorities’ (RTA) vehicles so that they meet state of good repair standards.
Program purpose and need statement:
Program performance:
Tracker target
  Not established - demand response vehicle age / revenue vehicle condition
PfP tool forecast
7.4 average fleet age in years (up from 4.9)
FY2019-2023 program budget:
$92.3 million over five years
Other indicators
  To be determined
Other indicators
  To be determined

## Slide 57: Modernization investments by program
Chart: 
| Transit / RTA Replacement Facilities | Transit / RTA Fleet Upgrades | Transit / RTA Facility and System Modernization | Registry / Alternative Service Channels/Kiosks | Registry / Customer Service Modernization | Registry / ATLAS | Rail / Track and Right-of-Way Modernization | Rail / Industrial Rail Access Program | Rail / Facility Modernization | MBTA / Process Improvements and Innovation | MBTA / Customer Experience and Technology | MBTA / AFC 2.0 | MBTA / Red Line/Orange Line Improvements | MBTA / Commuter Rail Safety and Resiliency | MBTA / Risk Management and Mitigation | MBTA / Accessibility | Information Technology / Workforce Productivity | Information Technology / Enterprise/BRP/Automation | Information Technology / Customer Digital Experience | Highway / Allston Multi-Modal | Highway / Roadway Reconstruction | Highway / Intersection Improvements | Highway / Intelligent Transportation Systems | Highway / Complete Streets | Highway / ADA Retrofits | Aeronautics / Airport Administration Buildings
Five-Year Program Size | 16400000 | 0 | 26300000 | 2250000 | 3775000 | 61500000 | 31112377 | 15000000 | 13250000 | 25000000 | 104000000 | 160000000 | 1565700000 | 637500000 | 177100000 | 265000000 | 14210000 | 19490000 | 10000000 | 16000000 | 1418625000 | 180787500 | 81562500 | 50000000 | 21825000 | 25000000
Five-year program budget in millions
Aeronautics / Airport administration buildings
Highway / ADA retrofits
Highway / Complete streets
Highway / Intelligent transportation systems
Highway / Intersection improvements
Highway / Roadway reconstruction
Highway / Allston multi-modal
Information Technology / Customer digital experience
Information Technology / Enterprise/BRP/automation
Information Technology / Workforce productivity
MBTA / Accessibility
MBTA / Risk Management and Mitigation
MBTA / Commuter Rail Safety and Resiliency
MBTA / Red Line/Orange Line Improvements
MBTA / AFC 2.0
MBTA / Customer Experience and Technology
MBTA / Process Improvements and Innovation
Rail / Facility modernization
Rail / Industrial rail access program
Rail / Track and right-of-way modernization
Registry / ATLAS
Registry / Customer service modernization
Registry / Kiosks
Transit / RTA facility and system modernization
Transit / RTA fleet upgrades
Transit / RTA replacement facilities
Aeronautics | Highway | IT | MBTA | Rail | RMV | Transit | Total SFY19-23
$25.0 (millions) | $1,768.8 | $43.7 | $2,934.3 | $59.4 | $67.5 | $42.7 | $4,941.4

## Slide 58: Modernization program for Aeronautics
Airport Administration Buildings
This program builds or renovates airport administration buildings as recommended by the 2010 Statewide Airport System Plan, which identified 17 airports that did not have existing, or adequate administration buildings. This program is necessary to provide sufficient administrative spaces in airports, which is integral to improving the safety, efficiency, and business growth of the airport asset.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2018-2022 program budget:
$25.0 million over five years
Other indicators
  Goal is to address one building per year with this funding level

## Slide 59: Modernization programs for Highway
ADA Retrofits
This program improves the condition and accessibility of state owned sidewalks. This program is necessary to meet obligations identified under the MassDOT ADA Transition Plan.
Program purpose and need statement:
Program performance:
Tracker target
  2018 – 40% reduction from FY 12
  2020 – 60% reduction from FY 12
  Long term - 0 failed or missing
PfP tool forecast
Under development
FY2019-2023 program budget:
$21.8 million over five years
Complete Streets
This program rewards communities that demonstrate a commitment to embedding Complete Streets in their policies and practices by providing them with technical assistance and funding.
Program purpose and need statement:
Program performance:
Tracker target
  Number of municipalities with approved Complete Streets policies
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$50.0 million over five years
Other indicators
Other indicators
  Number of Complete Streets policies to be enacted
  Number of failed or missing curb ramps on statewide inventory

## Slide 60
Intelligent Transportation Systems
This program supports innovative and new communication equipment and information technology systems (signs, cameras, sensors, etc.) designed to provide real time traffic information to residents and visitors. This program is necessary to improve our network of communication tools to allow drivers to make better informed decisions regarding travel options.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$81.6 million over five years
Intersection Improvements
This program upgrades and improves traffic signals and intersections. This program is necessary to meet safety improvement targets.
Program purpose and need statement:
Program performance:
Tracker target
  2018 – 0.63 fatalities; 6 injuries*
  2020 - 0.62 fatalities; 6 injuries*
  Long term – move to zero
PfP tool forecast
Under development
FY2019-2023 program budget:
$180.8 million over five years
Other indicators
Other indicators
  To be determined
  Travel time from Real Time Traffic Management (RTTM)
** Tracker target per 100 million vehicle miles traveled (VMT)
*Equivalent Property Damage Only

## Slide 61
Roadway Reconstruction
This program improves the overall condition of roads, by supporting both large and small state and municipal investments. Nearly all of the projects in this program include improvements to bicycle and pedestrian user spaces.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$1,418.6 million over five years
Allston Multi-Modal Implementation
This program reconstructs and realigns the Allston interchange to improve safety for all transportation modes: walking, cycling, driving, transit and to create a vibrant Allston neighborhood reconnecting sections to each other and to the Charles River.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$16 million over five years*
Other indicators
Other indicators
  To be determined
  Pavement condition; crash data
*For design and permitting; does not include construction.

## Slide 62: Modernization programs for IT
Customer Digital Experience
This program ensures that MassDOT and MBTA websites present clear, concise, and timely information to the public at all times. This program is necessary to ensure that transportation system users have successful interactions with MassDOT or MBTA public facing websites.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$10.0 million over five years
Enterprise / BPR* /
Automation
This program improves the ways that MassDOT manages and optimizes core functionality (such as document management, file shares, workflows, etc.) through business needs analysis and the implementation of enterprise solutions that are scalable, resilient and have an extensive ecosystem.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$19.5 million over five years
Other indicators
  Monitor budgets and scheduled deliverables. Help Desk and Incident Report activity 100% of websites updated and aligned with Commonwealth standards.
Other indicators
  Monitor budgets & scheduled deliverables. Full implementation of critical finance, HR and legal systems.
*Business Process Re-engineering

## Slide 63
Workforce Productivity
This program improves business processes through automated workflows and other electronic means at the department level. This program also may include investments that improve process timelines, reduce paperwork, and contribute to efficiency.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$14.2 million over five years
Other indicators
  Monitor budgets and scheduled deliverables. Full implementation of departmental business process and workflows.

## Slide 64: Modernization programs for MBTA
Accessibility
Risk Management and Mitigation
This program improves accessibility at MBTA commuter rail, subway and bus stations. This program is necessary to meet the goals of the Authority’s Plan for Accessible Transit Infrastructure (“PATI”).
Program purpose and need statement:
Program performance:
Tracker target
  Not established - platform accessibility
PfP tool forecast
87% of the stations ADA compliant by 2022
FY2019-2023 program budget:
$265.0 million over five years
This program implements risk management initiatives as well as proactive efforts to improve workplace safety and system security.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2018-2022 program budget:
$177.1 million over five years
Other indicators
Other indicators
  Implement MBTA Occupational Health and Safety Program
  Reduce barriers to accessibility

## Slide 65
Process Improvements and Innovation
Customer Experience and Technology
This program includes investments in business process improvements and innovations that enhance productivity or quality of MBTA services and capital programs.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$25.0 million over five years
This program includes improvement projects that modernize the system and enhance customer experience.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$104.0 million over five years
Other indicators
Other indicators
  Under development
  Under development

## Slide 66
AFC 2.0
Red Line/Orange Line Improvements
The AFC 2.0 program will implement a new reliable and convenient fare payment and collection system, integrated across all modes, to replace CharlieCards/Tickets and supporting hardware and software
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$160.0 million over five years
The Red Line and Orange Line Improvement program includes the set of vehicle and infrastructure investments needed to fully modernize the fleet and achieve the service goal of three minute headways on both lines.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$1,565.7 million over five years
Other indicators
Other indicators
Project-specific milestones
Project-specific milestones

## Slide 67
Commuter Rail Safety and Resiliency
This program includes projects that improve the safety and resiliency of the Commuter Rail network, including the implementation of Positive Train Control.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$637.5 million over five years
Other indicators
  Project-specific milestones

## Slide 68: Modernization programs for Rail
Facility modernization
This program repairs or replaces rail facilities, specifically rail yards and stations, to upgrade them to current industry standards or maintain the facility’s utility. Prioritization of projects in this program will reflect economic opportunities for the line served, condition reports, type of risk/usage, and any contractual or regulatory requirements for action and consistency with the Statewide Rail Plan. This program is necessary to maintain a safe, reliable, cost effective, and modern rail system.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$13.25 million over five years
Industrial Rail Access Program
This program makes investments in private sector rail lines to leverage private investment that will increase freight rail usage or will modernize an active line to increase the utility to customers.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$15.0 million over five years
Other indicators
Other indicators
  To be determined
  To be determined

## Slide 69
Track and right-of-way modernization
This program repairs or replaces assets within the rail right of way (typically ties, rail, ballast, switches, etc.) to upgrade their capacity to reflect current industry standards (ie: weight capacity to 286,000 lbs) for the line and maintain the line’s utility. Prioritization of projects in this program will reflect economic opportunities for the line, most recent inspections, type of usage (ie: hazardous cargo), any contractual or regulatory requirements for action, and consistency with the Statewide Rail Plan. A consultant has been retained to develop an asset management system for Rail that will be used to inform future investment decisions.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$31.1 million over five years
Other indicators
  To be determined

## Slide 70: Modernization programs for Registry
ATLAS
This program improves RMV service delivery options by replacing the ALARS system. This program is necessary to increase business process efficiency through reduced wait times, increase the number of transactions done via alternative customer service channels, and increase the capacity of third parties dependent on RMV data.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$61.5 million over five years
Customer service modernization
This program includes updating and upgrading leased branch locations to accommodate the new dual line queuing model, signage, furniture and fixtures.
Program purpose and need statement:
Program performance:
Tracker target
  Percent of Service Center customers served in 30 minutes or less. Reduces the percent of customers served in Service Centers statewide waiting 60 minutes or more to be served.
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$3.8 million over five years
Other indicators
  Modernizing the RMV’s Service Centers through wayfinding, queuing systems, and appropriate layouts is a critical element in meeting wait time and customer service performance standards.
Other indicators
  ATLAS replaces the 30 year old mainframe system known as ALARS. ALARS is dated in technical and user interface terms, is expensive to maintain and lacks flexibility to update as business requirements change.

## Slide 71
Alternative Service Channels/Kiosks
This program supports customer use of alternative service channels, including self-serve kiosks which may be introduced in FY2020-FY2021. Serving customers outside of an RMV Service Center is critical to meeting wait time goals
Program purpose and need statement:
Program performance:
Tracker target
  Percent of system-wide transactions conducted outside of Service Centers
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$2.25 million over five years
Other indicators
  Online transaction options, 3rd parties, and kiosks help to increase the number of customers served in Service Centers in 30 minutes or less by decreasing the customer volume of in-person visits.

## Slide 72: Modernization programs for Transit
RTA facility and system modernization
This program improves or modernizes existing RTA facilities, systems or equipment.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$26.3 million over five years
RTA fleet upgrades
This program allows for Regional Transit Authority fleet growth. This program is necessary to meet service needs or expansion.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$0.0 million over five years
Other indicators
Other indicators
  To be determined
  To be determined

## Slide 73
RTA Replacement Facilities
This program constructs modernized RTA maintenance, administrative, operations or intermodal facilities.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$16.4 million over five years
Other indicators
  To be determined

## Slide 74: Expansion investments by program
Chart: 
| Rail / Vehicle Expansion | Rail / Track and Right-of-Way Expansion | Rail/MBTA / South Coast Rail | MBTA / Expansion Projects | MBTA / Green Line Extension | Highway / Capacity | Highway / Bicycle and Pedestrian | OTP / Bicycle and Pedestrian Modal Implementation
Five-Year Program Size | 31000000 | 0 | 108000000 | 58000000 | 1364500000 | 308137000 | 180562500 | 60000000
Five-year program budget in millions
OTP / Bicycle and Pedestrian Modal Implementation
Highway / Bicycle and pedestrian
Highway / Capacity
MBTA / Green Line Extension
MBTA** / Expansion projects
Rail/MBTA* / South Coast Rail
Rail / Track and right-of-way expansion
Rail / Vehicle expansion
Highway | MBTA* | Rail* | OTP | Total SFY19-23
$488.7 (millions) | $1,422.5 | $139.0 | $60.0 | $2,110.2

## Slide 75: Expansion programs for Highway
Bicycle and Pedestrian
This program constructs multi-use paths and other trails that are independent from a roadway. In addition, this program will meet future needs identified through the ongoing statewide bicycle and pedestrian planning efforts.
Program purpose and need statement:
Program performance:
Tracker target
  Under development
PfP tool forecast
1,041 miles of off-road bicycle and pedestrian facilities
FY2019-2023 program budget:
$180. 6 million over five years
Capacity
This program adds new connections or expands the existing transportation network.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$308.1 million over five years
Other indicators
  To be determined
Other indicators
  To be determined

## Slide 76: Expansion programs for MBTA
Expansion Projects
Green Line Extension
This program makes investments in targeted expansions in order to improve access to transit, including the Silver Line to Chelsea and Blue Hill Avenue Station on the Fairmount Line and South Coast Rail.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$58.0 million over five years
The Green Line Extension program includes the vehicles, stations and infrastructure to extend the Green Line from a relocated Lechmere Station in East Cambridge to Union Square in Somerville and College Avenue in Medford.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$1,364.5 million over five years
Other indicators
Other indicators
  To be determined
  To be determined

## Slide 77: Expansion programs for OTP
Bicycle and Pedestrian Multi-Modal Implementation
This program will meet needs identified through the statewide bicycle and statewide pedestrian planning efforts. The plans address critical needs around safety, accessibility, network connectivity and maintenance.
Program purpose and need statement:
Program performance:
Tracker target
Under development
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$60.0 million over five years
Other indicators
  To be determined

## Slide 78: Expansion programs for Rail
Track and right-of-way expansion
Vehicles expansion
This program repairs or replaces assets within the rail right of way (typically ties, rail, ballast, switches, etc.) to expand existing rail services, including the addition of passenger rail or freight rail. Prioritization of projects in the program will reflect economic opportunities for the new service, consistency with the Statewide Rail Plan, and any contractual or regulatory requirements for action.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP
FY2019-2023 program budget:
$0.0 million over five years
This program repairs, replaces, or acquires rail equipment (locomotives, coaches, ballast cars, light duty vehicles, etc.) to expand existing rail services, including the addition of passenger rail or freight rail. Prioritization will reflect economic opportunities for the new service, consistency with the Statewide Rail Plan, and any contractual or regulatory requirements for action.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019-2023 program budget:
$31.0 million over five years
Other indicators
Other indicators
  To be determined
  To be determined

## Slide 79
South Coast Rail
This program funds the Commonwealth’s commitment to move forward with the South Coast Rail project to serve the existing and future demand for public transportation between Fall River/New Bedford and Boston, and to enhance regional mobility and support smart growth planning and development strategies in Southeastern Massachusetts.
Program purpose and need statement:
Program performance:
Tracker target
  Not established in Tracker
PfP tool forecast
Not forecasted in PfP tool
FY2019 program budget:*
$ 108.0 million
Other indicators
  To be determined
*Pending development of finance plan; includes FY 19 SCR program budget for both Rail and MBTA program.

## Slide 80: About project lists
The full list of investments is presented by Division. The information within each column is described below:
Location – where the investment is located
Project ID – the Division specific ID that uniquely identifies each investment
Project name – the name of the investment and a brief description
Priority – the capital priority that the investment addresses
Program – the program from which the investment is made
Score – the score of the investment (reliability investments are not scored)
Total cost – the total cost of the investment
Prior years – the spending on the investment that pre-dates the plan update
FY 2019 – the spending estimated to occur in fiscal year 2019
FY 2020-2023 – the spending estimated to occur in the out years of the plan
Post-CIP – the spending estimated to occur beyond the plan horizon

## Slide 81: Equity analysis
The social equity analysis was conducted to establish compliance with federal and state nondiscrimination laws and regulations, including Title VI of the Civil Rights Act of 1964 (Title VI), the Civil Rights Restoration Act of 1987, and the 1994 Presidential Executive Order 12898 on Environmental Justice. The analysis evaluated investments per capita at the municipal level due to the methodology used to create the CIP’s project universe. While municipalities were the only geographic level analyzed, equitable investment was evaluated using a number of different variables and indicators. The most significant variables used to draw conclusions are:
  MassDOT investments, which incorporates all capital investments within MassDOT’s divisions; and
  All CIP investments, which includes all of the capital investments within both MassDOT and the MBTA.
Equity analysis in process

## Slide 82: Geographic equity
As a state agency, MassDOT seeks to fund transportation infrastructure equitably across the state. However, because of the data that is available and the nature of transportation infrastructure, there is no clear consensus on what exactly is an equitable distribution of resources, given the variation between needs, demand, and contributed tax dollars. As a result, MassDOT assessed the data in a variety of ways for this equity analysis. The maps included in this section illustrate a few different ways that MassDOT assessed the data. While no single method is perfect, these approaches, taken together, provide useful information to better understand the regional distribution of resources. Since this Capital Investment Plan is a one year update, projects currently underway are excluded from the analysis. Only projects programmed within SFY 2019-2023 in the Plan are considered.
Some of the variables considered in analyzing the geographic equity of the plan include population, lane miles, Chapter 90 ratio, and Regional Transit Authority (RTA) ridership. Population is considered to evaluate investment per capita and lane miles is considered as a proxy to evaluate demand for roadway maintenance and improvements. Similarly, RTA ridership is used as a proxy to measure the need and demand of transit investments.
The Chapter 90 Program is a formula program distributed to municipalities for roadway improvements based on population (20.83%), employment (20.83%), and lane miles (58.33%). This formula can serve as a benchmark against which MassDOT Highway funding should be distributed and as a proxy for an appropriation distribution for all non-transit MassDOT projects. Because of concerns with just looking at population or at lane miles, this formula is an opportunity to consider both variables. As the formula is already in use throughout the Commonwealth, MassDOT opted to use the given percentages as an acceptable measure for an equitable distribution of investments.
Analysis and update in process